Eightieth session

Items 137 and 138 of the preliminary list*

Proposed programme budget for 2026

Programme planning

Proposed programme budget for 2026

Part V

Regional cooperation for development

Section 22

Economic and social development in Western Asia

Programme 19

Economic and social development in Western Asia

Contents

|  |  |  | Page |
| --- | --- | --- | --- |
| - Proposed programme plan for 2026 and programme performance in 2024** |  |  | 3 |
| Overall orientation |  |  | 3 |
| Programme of work |  |  | 12 |
| Subprogramme 1. Climate change and natural resource sustainability |  |  | 12 |
| Subprogramme 2. Gender justice, population and inclusive development |  |  | 17 |
| Subprogramme 3. Shared economic prosperity |  |  | 21 |
| Subprogramme 4. Statistics, the information society and technology |  |  | 26 |
| Subprogramme 5. 2030 Agenda and SDG coordination |  |  | 30 |
| Subprogramme 6. Governance and conflict prevention |  |  | 34 |

*	A/80/50.

**	In keeping with paragraph 10 of General Assembly resolution 77/267, the part consisting of the programme plan and programme performance information (part II) is submitted through the Committee for Programme and Coordination for the consideration of the Assembly.

| - Proposed post and non-post resource requirements for 2026*** | 40 |
| --- | --- |
| Overview | 40 |
| Policymaking organs | 47 |
| Executive direction and management | 49 |
| Programme of work | 51 |
| Subprogramme 1. Climate change and natural resource sustainability | 51 |
| Subprogramme 2. Gender justice, population and inclusive development | 52 |
| Subprogramme 3. Shared economic prosperity | 53 |
| Subprogramme 4. Statistics, the information society and technology | 54 |
| Subprogramme 5. 2030 Agenda and SDG coordination | 55 |
| Subprogramme 6. Governance and conflict prevention | 56 |
| Programme support | 57 |
| Annexes |  |
| - Organizational structure and post distribution for 2026 | 59 |
| - Summary of proposed post changes, by component and subprogramme | 62 |

***	In keeping with paragraph 10 of General Assembly resolution 77/267, the part consisting of the post and non-post resource requirements (part III) is submitted through the Advisory Committee on Administrative and Budgetary Questions for the consideration of the Assembly.

A.	Proposed programme plan for 2026 and programme performance in 2024

Overall orientation

Mandates and background

22.1	The Economic and Social Commission for Western Asia (ESCWA) is responsible for promoting inclusive and sustainable development in the Arab region. The mandate derives from the priorities established in relevant General Assembly and Economic and Social Council resolutions and decisions, including Council resolution 1818 (LV), by which the Commission was established, and resolution 1985/69, by which its terms of reference were amended to emphasize its social functions. The Commission’s membership includes 21 Arab member States.

22.2	The adoption of the Pact for the Future (see General Assembly resolution 79/1) provides a crucial opportunity to redefine the trajectory of the Arab region, which, notwithstanding its potential and human capital, is still not on track to implement the 2030 Agenda for Sustainable Development and achieve all its Sustainable Development Goals. The development gains achieved to date continue to be jeopardized by conflict, which, in some cases, has set back decades-long progress; political instability and social unrest; governance, social and economic challenges; and the impact of a changing climate on ecosystems. The Pact for the Future offers the region another chance to harness artificial intelligence, digital innovation and predictive analytics, in line with the Global Digital Compact, to address the complex and interrelated challenges that it faces, including economic volatility, social inequalities, conflict and the impacts of climate change, and to take decisive action towards achieving the aspirations of the people of the Arab region for a prosperous future for all. Given its regional mandate, ESCWA is uniquely positioned to support national development trajectories and priorities by leveraging its expertise, toolkits and partnerships, in support of jointly owned development solutions and outcomes. The support delivered by the Commission to member States is also provided through the regular programme of technical cooperation and Development Account projects.

Strategy and external factors for 2026

22.3	The Commission’s programme of work for 2026 remains guided by universal principles and rights, aligned with its mandates and centred around tailored and timely support to member States in their efforts to achieve the Sustainable Development Goals. To deliver on this commitment, ESCWA will continue to provide evidence-based, novel policy options, underpinned by analysis made possible by its suite of interactive, data-driven modelling and policy simulation tools and knowledge repositories; to provide technical advice and enhance human and institutional capacities, including through peer-to-peer exchanges and the promotion of South-South and interregional collaboration; to leverage its convening role to promote inclusive dialogue at the national, subregional and intraregional and interregional levels and forge consensus on viable development solutions; and to advocate for whole-of-government and whole-of-society approaches to accelerate progress against the Goals and their targets, while championing the region’s perspective through a global lens. The programme of work remains focused on high-impact interventions as means of achieving inclusive and equitable development outcomes, which address the specific needs of groups in vulnerable situations, including women, young people, older persons, persons with disabilities and the diverse and specific challenges of least developed and middle-income countries and countries in conflict, in line with the Doha Programme of Action for the Least Developed Countries for the decade 2022–2031.

22.4	As defined by the objectives of the six subprogrammes, the Commission’s programme of work remains focused on areas such as climate action and the integrated management of water resources; the transition to new and renewable sources of energy, sustainable food systems and circular economy approaches; multidimensional poverty reduction and inclusive social protection; social and gender justice, women’s economic empowerment and improved access to labour markets, as part of the commitment to “leave no one behind”; macroeconomic, fiscal and trade policies, competitiveness of business environments and opportunities for small and medium-sized enterprises; improved access to innovative sources of development finance and sustainable debt management; information technology and statistics; the transparency and accessibility of public institutions, including through digitization; innovation and digital transformation; and governance, the assessment and mitigation of transboundary risks, including conflict, and boosting the effectiveness and efficiency of public administration.

22.5	With regard to cooperation with other entities at the global, regional, national and local levels, ESCWA will sustain its strategic partnership with the League of Arab States, the Organisation for Economic Co-operation and Development/Development Assistance Committee and other intergovernmental organizations, as well as the Islamic Development Bank, the Arab Fund for Economic and Social Development and other relevant financial institutions. It will also promote South-South and triangular cooperation and further enhance its outreach to academic institutions and think tanks, civil society organizations and the private sector. New partnership opportunities will also be pursued as a means of expanding the range of the Commission’s support to member States, including by facilitating access to innovation, new technologies and funding opportunities.

22.6	With regard to inter-agency coordination and liaison, as outlined in General Assembly resolution 72/279, the Commission will continue to discharge its role as co-coordinator of the Regional Collaborative Platform for Arab States and its subsidiary issue-based coalitions. It will also work closely with the Development Coordination Office, the resident coordinator offices of the United Nations, United Nations country teams, the World Bank, the United Nations Conference on Trade and Development and the United Nations Industrial Development Organization to ensure that any support that it provides to member States is relevant, timely and effective and fully aligned with the commitments outlined within the national United Nations Sustainable Development Cooperation Frameworks, while avoiding duplication of interventions and gaps.

22.7	With regard to the external factors, the overall plan for 2026 is based on the following planning assumptions:

(a)	Sufficient opportunities for protecting and leveraging development gains for further progress towards the implementation of the 2030 Agenda exist, notwithstanding the volatile global, regional and national landscapes and increased need for urgent humanitarian action and peacebuilding efforts;

(b)	Member States remain engaged and committed to collaborating on a range of sustainable development initiatives, with a focus on transboundary issues and emerging challenges;

(c)	Development partners remain committed to collaboration on and the joint implementation of development initiatives, including their prioritization, the identification of innovative solutions and opportunities for specific contributions;

(d)	The Commission’s operational preparedness and adaptability enable it to maintain business continuity, also during times of compromised safety and security emerging from conflict, political and social instability and/or natural disasters.

22.8	ESCWA integrates a gender perspective into its activities, deliverables and results, as appropriate. This includes the provision of support to its member States in developing inclusive, gender-sensitive policy frameworks to address a wide range of economic and social issues and in enhancing the capacities of national institutions and actors, as well as the development of publications and technical materials specific to advancing gender equality and women’s economic empowerment in the region. The Commission’s commitment to gender equality remains in line with the United Nations global accountability framework, in accordance with Economic and Social Council resolution 2023/11.

22.9	In line with the United Nations Disability Inclusion Strategy, ESCWA will continue to make policy recommendations available to member States and advocate in favour of the adoption of national frameworks that promote the greater inclusion and empowerment of persons with disabilities, including enhanced access to labour markets and basic social services.

22.10	ESCWA will integrate issues related to older persons and young people across its programme of work with the aim of augmenting their role as active contributors to the implementation of the 2030 Agenda. In this context the Commission will: (a) promote their meaningful participation and inclusion in development dialogues; (b) generate and disseminate knowledge essential for the development of policies that are responsive to the needs of young people and older persons; (c) facilitate peer-to-peer learning among member States within the region and beyond; and (d) support member States in the adoption and implementation of polices that protect the rights of young people and older persons.

Legislative mandates

22.11	The list below, which was reviewed in the preparation of the proposed programme budget, provides all mandates entrusted to the programme:

General Assembly resolutions

| 68/196 | United Nations Guiding Principles on Alternative Development |
| --- | --- |
| 68/211 | International Strategy for Disaster Reduction |
| 69/277 | Political declaration on strengthening cooperation between the United Nations and regional and subregional organizations |
| 69/313 | Addis Ababa Action Agenda of the Third International Conference on Financing for Development |
| 70/1 | Transforming our world: the 2030 Agenda for Sustainable Development |
| 71/313 | Work of the Statistical Commission pertaining to the 2030 Agenda for Sustainable Development |
| 72/279 | Repositioning of the United Nations development system in the context of the quadrennial comprehensive policy review of operational activities for development of the United Nations system |
| 74/230 | Culture and sustainable development |
| 75/4 | Special session of the General Assembly in response to the coronavirus disease (COVID-19) pandemic |
| 76/258 | Doha Programme of Action for the Least Developed Countries |
| 78/1 | Political declaration of the high-level political forum on sustainable development convened under the auspices of the General Assembly |
| 79/1 | The Pact for the Future |
| 79/12 | Cooperation between the United Nations and the League of Arab States |
| 79/199 | Follow-up to and implementation of the outcomes of the International Conferences on Financing for Development |
| 79/202 | Promoting sustainable consumption and production patterns for the implementation of the 2030 Agenda for Sustainable Development, building on Agenda 21 |
| 79/225 | Eradicating rural poverty to implement the 2030 Agenda for Sustainable Development |
| 79/226 | Quadrennial comprehensive policy review of operational activities for development of the United Nations system |
| 79/228 | Towards global partnerships: a principle-based approach to enhanced cooperation between the United Nations and all relevant partners |
| 79/236 | South-South cooperation |

Economic and Social Council resolutions

| 1818 (LV) | Establishment of an Economic Commission for Western Asia |
| --- | --- |
| 1985/69 | Amendment of the terms of reference of the Economic Commission for Western Asia: change of name of the Commission |
| 2011/5 | The role of the United Nations system in implementing the internationally agreed goals and commitments in regard to gender equality and the empowerment of women |
| 2014/36 | Redesignation of the Technical Committee of the Economic and Social Commission for Western Asia as the Executive Committee and amendment of its terms of reference |
| 2015/10 | 2020 World Population and Housing Census Programme |
| 2016/10 | Economic and Social Commission for Western Asia strategy and plan of action on the 2030 Agenda for Sustainable Development |
| 2017/7 | Work of the Statistical Commission pertaining to the 2030 Agenda for Sustainable Development |
| 2020/5 | Strengthening coordination of the statistical programmes in the United Nations system |
| 2021/3 | New strategic vision of the Economic and Social Commission for Western Asia |
| 2022/23 | Situation of and assistance to Palestinian women |
| 2024/19 | Progress in the implementation of General Assembly resolution 75/233 on the quadrennial comprehensive policy review of operational activities for development of the United Nations system |

Economic and Social Commission for Western Asia ministerial declarations and resolutions

| Tunis Declaration on Social Justice in the Arab Region (2014) |  |
| --- | --- |
| Doha Declaration on the Implementation of the 2030 Agenda for Sustainable Development (2016) |  |
| Beirut Consensus on Technology for Sustainable Development in the Arab Region (2018) |  |
| Arab Declaration on Progress in Implementation of the Beijing Declaration and Platform for Action after 25 Years (2019) |  |
| 286 (XXV) | Gender statistics for equality and empowerment of women |
| 296 (XXVI) | Enhancing public sector institutions and resources to attain national development goals |
| 331 (XXX) | Comprehensive approaches to technical cooperation in response to member States’ emerging needs |
| 334 (XXX) | Adoption of the reports of the subsidiary bodies of the Economic and Social Commission for Western Asia |
| 335 (S-VI) | Programme Plan for the Economic and Social Commission for Western Asia for 2021 |
| 337 (S-VII) | Request from Djibouti for membership of the Economic and Social Commission for Western Asia |
| 341 (S-VII) | Adoption of the session reports of subsidiary bodies of the Economic and Social Commission for Western Asia |
| 343 (XXXI) | Programme plan of the Economic and Social Commission for Western Asia for 2025 |
| 344 (XXXI) | Frequency of the sessions of the Committee on Social Development of the Economic and Social Commission for Western Asia |
| 345 (XXXI) | War on Gaza and support for the Palestinian people |
| 346 (XXXI) | Effective economic governance and modernization of public administration |

Subprogramme 1

Climate change and natural resource sustainability

General Assembly resolutions

| 71/222 | International Decade for Action, “Water for Sustainable Development,” 2018–2028 |
| --- | --- |
| 72/178 | The human rights to safe drinking water and sanitation |
| 72/242 | Impact of rapid technological change on the achievement of the Sustainable Development Goals |
| 73/226 | Midterm comprehensive review of the implementation of the International Decade for Action “Water for Sustainable Development”, 2018–2028 |
| 74/215 | Agricultural technology for sustainable development |
| 75/212 | United Nations Conference on the Midterm Comprehensive Review of the Implementation of the Objectives of the International Decade for Action, “Water for Sustainable Development,” 2018–2028 |
| 75/219; 79/208 | Implementation of the Convention on Biological Diversity and its contribution to sustainable development |
| 75/271 | Nature knows no borders: transboundary cooperation a key factor for biodiversity conservation, restoration and sustainable use |
| 75/280 | International meeting entitled “Stockholm+50: a healthy planet for the prosperity of all – our responsibility, our opportunity” |
| 76/300 | The human right to a clean, healthy and sustainable environment |
| 77/294 | International Day of Combating Sand and Dust Storms |
| 78/314 | United Nations Decade on Combating Sand and Dust Storms (2025–2034) |
| 78/327 | Modalities of the 2026 United Nations Water Conference to Accelerate the Implementation of Sustainable Development Goal 6: Ensure availability and sustainable management of water and sanitation for all |
| 79/171 | The right to food |
| 79/205 | Disaster risk reduction |
| 79/206 | Protection of global climate for present and future generations of humankind |
| 79/207 | Implementation of the United Nations Convention to Combat Desertification in Those Countries Experiencing Serious Drought and/or Desertification, Particularly in Africa |
| 79/211 | Ensuring access to affordable, reliable, sustainable and modern energy for all |
| 79/212 | Combating sand and dust storms |
| 79/227 | Agriculture development, food security and nutrition |

Economic and Social Commission for Western Asia resolutions

| 281 (XXV) | Addressing climate change issues in the Arab region |
| --- | --- |
| 305 (XXVII) | Sustainable development in the region and follow-up and implementation of the decisions of the Rio+20 Conference |
| 329 (XXX) | Establishment of the Arab centre for climate change policies in the Arab region |
| 339 (S-VII) | Establishment of a centre for advancing carbon emissions reduction under the Commission |

United Nations Environment Assembly of the United Nations Environment Programme resolution

| 5/11 | Enhancing circular economy as a contribution to achieving sustainable consumption and production |
| --- | --- |

Subprogramme 2

Gender justice, population and inclusive development

General Assembly resolutions

| 66/130 | Women and political participation |
| --- | --- |
| 66/131 | Convention on the Elimination of All Forms of Discrimination against Women |
| 68/143 | Assistance to refugees, returnees and displaced persons in Africa |
| 68/181 | Promotion of the Declaration on the Right and Responsibility of Individuals, Groups and Organs of Society to Promote and Protect Universally Recognized Human Rights and Fundamental Freedoms: protecting women human rights defenders |
| 68/191 | Taking action against gender-related killing of women and girls |
| 68/239 | Implementation of the outcome of the United Nations Conference on Human Settlements (Habitat II) and strengthening of the United Nations Human Settlements Programme (UN-Habitat) |
| 69/236 | World Survey on the Role of Women in Development |
| 71/256 | New Urban Agenda |
| 73/195 | Global Compact for Safe, Orderly and Regular Migration |
| 74/120 | Promoting social integration through social inclusion |
| 74/121 | Policies and programmes involving youth |
| 74/126 | Improvement of the situation of women and girls in rural areas |
| 74/127 | Violence against women migrant workers |
| 74/128 | Follow-up to the Fourth World Conference on Women and full implementation of the Beijing Declaration and Platform for Action and the outcome of the twenty-third special session of the General Assembly |
| 74/134 | The girl child |
| 74/144 | Implementation of the Convention on the Rights of Persons with Disabilities and the Optional Protocol thereto: accessibility |
| 74/148 | Protection of migrants |
| 74/253 | Enhancing accessibility for persons with disabilities to conferences and meetings of the United Nations system |
| 78/195 | Implementation of the Convention on the Rights of Persons with Disabilities and the Optional Protocol thereto: situations of risk and humanitarian emergencies |
| 78/318 | Modalities of the “World Social Summit”, under the title “the Second World Summit for Social Development” |
| 79/146 | Implementation of the outcome of the World Summit for Social Development and of the twenty-fourth special session of the General Assembly |
| 79/147 | Follow-up to the Second World Assembly on Ageing |
| 79/149 | Inclusive development for and with persons with disabilities |
| 79/152 | Intensification of efforts to prevent and eliminate all forms of violence against women and girls: the digital environment |
| 79/217 | International migration and development |
| 79/221 | Implementation of the Third United Nations Decade for the Eradication of Poverty (2018–2027) |
| 79/223 | Women in development |

Security Council resolutions

| 1325 (2000) |  |
| --- | --- |
| 2535 (2020) |  |

Economic and Social Council resolutions

| 2014/5 | Promoting empowerment of people in achieving poverty eradication, social integration and full employment and decent work for all |
| --- | --- |
| 2015/21 | Taking action against gender-related killing of women and girls |
| 2017/12 | Promoting the rights of persons with disabilities and strengthening the mainstreaming of disability in the implementation of the 2030 Agenda for Sustainable Development |
| 2019/6 | Addressing inequalities and challenges to social inclusion through fiscal, wage and social protection policies |
| 2020/7 | Affordable housing and social protection systems for all to address homelessness |
| 2020/15 | Multi-year programme of work of the Commission on the Status of Women |
| 2021/8 | Future organization and methods of work of the Commission for Social Development |
| 2024/3 | Mainstreaming a gender perspective into all policies and programmes in the United Nations system |
| 2024/4 | Promoting care and support systems for social development |
| 2024/6 | Fostering social development and social justice through social policies to accelerate progress on the implementation of the 2030 Agenda for Sustainable Development and to achieve the overarching goal of poverty eradication |

Economic and Social Commission for Western Asia ministerial declarations and resolutions

| Muscat Declaration: Towards the Achievement of Gender Justice in the Arab Region (2016) |  |
| --- | --- |
| Arab Declaration on Progress in the Implementation of the Beijing Declaration and Platform for Action after 25 Years (2019) |  |
| 304 (XXVII) | The role of participation and social justice in achieving sustainable development |

Subprogramme 3

Shared economic prosperity

General Assembly resolutions

| 69/213 | Role of transport and transit corridors in ensuring international cooperation for sustainable development |
| --- | --- |
| 77/175 | Role of the United Nations in promoting development in the context of globalization and interdependence |
| 78/139 | Financial inclusion for sustainable development |
| 78/148 | Strengthening the links between all modes of transport to achieve the Sustainable Development Goals |
| 78/162 | Development cooperation with middle-income countries |
| 78/271 | Further modalities of the Fourth International Conference on Financing for Development |
| 78/290 | Improving global road safety |
| 79/117 | Report of the United Nations Commission on International Trade Law on the work of its fifty-seventh session |
| 79/170 | The right to development |
| 79/195 | International trade and development |
| 79/196 | International financial system and development |
| 79/197 | External debt sustainability and development |
| 79/198 | Promoting investments for sustainable development |
| 79/201 | Entrepreneurship for sustainable development |
| 79/213 | Promoting the social and solidarity economy for sustainable development |
| 79/215 | Towards a New International Economic Order |
| 79/216 | Role of the United Nations in promoting development in the context of globalization and interdependence |
| 79/234 | Promotion of international cooperation to combat illicit financial flows and strengthen good practices on assets return to foster sustainable development |
| 79/235 | Promotion of inclusive and effective international tax cooperation at the United Nations |

Economic and Social Commission for Western Asia resolutions

| 214 (XIX) | Establishment of a technical committee on liberalization of foreign trade and economic globalization in the countries of the ESCWA region |
| --- | --- |
| 303 (XXVII) | Towards enhancing the macroeconomic policy in ESCWA member countries |
| 308 (XXVII) | The regional dimension of development |
| 313 (XXVII) | Frequency of sessions of the Technical Committee on Liberalization of Foreign Trade, Economic Globalization and Financing for Development in the Countries of the ESCWA Region |
| 332 (XXX) | Developing the work of the Technical Committee on Liberalization of Foreign Trade, Economic Globalization and Financing for Development |
| 338 (S-VII) | Establishment of an Arab integrated road safety observatory |

Subprogramme 4

Statistics, the information society and technology

General Assembly resolutions

| 68/261 | Fundamental Principles of Official Statistics |
| --- | --- |
| 69/282 | World Statistics Day |
| 70/125 | Outcome document of the high-level meeting of the General Assembly on the overall review of the implementation of the outcomes of the World Summit on the Information Society |
| 74/229 | Science, technology and innovation for sustainable development |
| 75/316 | Impact of rapid technological change on the achievement of the Sustainable Development Goals and targets |
| 78/311 | Enhancing international cooperation on capacity-building of artificial intelligence |

Economic and Social Council resolutions

| 2006/6 | Strengthening statistical capacity |
| --- | --- |
| 2011/24 | Committee of Experts on Global Geospatial Information Management |
| 2013/21 | Fundamental Principles of Official Statistics |
| 2014/35 | Establishment of an intergovernmental committee on technology for development in the Economic and Social Commission for Western Asia |
| 2019/19 | Promoting technical assistance and capacity-building to strengthen national measures and international cooperation to combat cybercrime, including information-sharing |
| 2019/24 | Assessment of the progress made in the implementation of and follow-up to the outcomes of the World Summit on the Information Society |
| 2020/13 | Science, technology and innovation for development |

Economic and Social Commission for Western Asia resolutions

| 276 (XXIV); 287 (XXV) | Strengthening statistical capacities in the ESCWA region |
| --- | --- |
| 283 (XXV) | ESCWA member country compliance with international standards for enhancing national statistical systems |
| 294 (XXVI) | Establishment of the ESCWA technology centre |
| 306 (XXVII) | Development of the Arab Internet Governance Forum process and sustaining efforts in the Arabic domain names field |

Subprogramme 5

2030 Agenda and SDG coordination

General Assembly resolutions

| 67/290 | Format and organizational aspects of the high-level political forum on sustainable development |
| --- | --- |
| 70/299 | Follow-up and review of the 2030 Agenda for Sustainable Development at the global level |
| 75/290 A; 75/290 B | Review of the implementation of General Assembly resolution 72/305 on the strengthening of the Economic and Social Council |

Economic and Social Commission for Western Asia resolutions

| 314 (XXVIII) | The Arab Forum on Sustainable Development |
| --- | --- |
| 327 (XXIX) | Working mechanisms of the Arab Forum for Sustainable Development |

Subprogramme 6

Governance and conflict prevention

General Assembly resolutions and decisions

| 35/63 | Restrictive business practices |
| --- | --- |
| 39/248 | Consumer protection |
| 57/337 | Prevention of armed conflict |
| 58/4 | United Nations Convention against Corruption |
| 68/303 | Strengthening the role of mediation in the peaceful settlement of disputes, conflict prevention and resolution |
| 69/228 | Promoting and fostering the efficiency, accountability, effectiveness and transparency of public administration by strengthening supreme audit institutions |
| 69/291; 75/327 | Implementation of the recommendations contained in the report of the Secretary-General on the causes of conflict and the promotion of durable peace and sustainable development in Africa |
| 69/327 | Promoting inclusive and accountable public services for sustainable development |
| 70/186 | Consumer protection |
| 75/201 | Review of the United Nations peacebuilding architecture |
| 77/22 | Committee on the Exercise of the Inalienable Rights of the Palestinian People |
| 77/216 | Promotion of peace as a vital requirement for the full enjoyment of all human rights by all |
| 79/81 | Peaceful settlement of the question of Palestine |
| 79/82 | Division for Palestinian Rights of the Secretariat |
| 79/83 | The Syrian Golan |
| 79/90 | The occupied Syrian Golan |
| 79/141 | Assistance to the Palestinian people |
| 79/163 | The right of the Palestinian people to self-determination |
| 79/229 | Permanent sovereignty of the Palestinian people in the Occupied Palestinian Territory, including East Jerusalem, and of the Arab population in the occupied Syrian Golan over their natural resources |

Security Council resolutions

| 1947 (2010) |  |
| --- | --- |
| 2429 (2018) |  |
| 2461 (2019) |  |
| 2558 (2020) |  |

Economic and Social Council resolutions

| 2023/28 | Report of the Committee of Experts on Public Administration on its twenty-second session |
| --- | --- |
| 2023/34 | Economic and social repercussions of the Israeli occupation on the living conditions of the Palestinian people in the Occupied Palestinian Territory, including East Jerusalem, and the Arab population in the occupied Syrian Golan |
| 2023/35 | Situation of and Assistance to Palestinian Women |

Economic and Social Commission for Western Asia resolutions

| 271 (XXIV) | Strengthening the role of ESCWA in addressing the impact of conflict and instability within the context of social and economic development |
| --- | --- |
| 282 (XXV) | Mitigating the impact on development of conflict, occupation and instability in ESCWA member countries |
| 292 (XXVI) | Upgrading the Section for Emerging and Conflict-Related Issues to the level of a division and establishing a governmental committee on emerging issues and development in conflict settings |
| 307 (XXVII); 316 (XXVIII); 330 (XXX) | Support for the Palestinian people |
| 326 (XXIX) | Justice for the Palestinian people: fifty years of Israeli occupation |

Deliverables

22.12	Table 22.1 lists all cross-cutting deliverables of the programme.

Table 22.1

Cross-cutting deliverables for the period 2024–2026, by category and subcategory

| Category and subcategory | 2024 planned | 2024 actual | 2025 planned | 2026 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Parliamentary documentation (number of documents) | 10 | 10 | 10 | 10 |
| 1. ESCWA ministerial session | – | – | – | 6 |
| 2. Executive Committee | 10 | 10 | 10 | 4 |
| Substantive services for meetings (number of three-hour meetings) | 15 | 14 | 17 | 15 |
| 3. ESCWA ministerial session (special session) | – | – | – | 4 |
| 4. Executive Committee | 6 | 6 | 8 | 4 |
| 5. ESCWA Advisory Committee | 2 | 2 | 2 | 1 |
| 6. Committee for Programme and Coordination | 1 | 1 | 1 | 1 |
| 7. Advisory Committee on Administrative and Budgetary Questions | 1 | 1 | 1 | 1 |
| 8. Fifth Committee | 1 | 1 | 1 | 1 |
| 9. Regional Collaborative Platform for Arab States | 4 | 3 | 4 | 3 |
| B. Generation and transfer of knowledge |  |  |  |  |
| Publications (number of publications) | 1 | – | 2 | – |
| 10. ESCWA annual report | 1 | – | – | – |
| 11. System-wide annual results report | – | – | 1 | – |
| 12. Report on megatrends (artificial intelligence) | – | – | 1 | – |
| C. Substantive deliverables |  |  |  |  |
| Databases and substantive digital materials: the Manara and ESCWA Learn platforms. |  |  |  |  |
| D. Communication deliverables |  |  |  |  |
| Outreach programmes, special events and information materials: selected international days; the Arab Forum for Sustainable Development; the Arab summit for small and medium-sized enterprises and the Arab Forum for Equality; and awareness-raising activities on the work of the United Nations and ESCWA. |  |  |  |  |
| External and media relations: briefings by the Executive Secretary and other senior officials; ESCWA livestreaming services; and press releases on and media coverage of ESCWA activities. |  |  |  |  |
| Digital platforms and multimedia content: videos and other visual content on ESCWA activities and daily ESCWA news on the ESCWA website and social media accounts; and ESCWApod. |  |  |  |  |

Evaluation activities

22.13	The following evaluations completed in 2024 have guided the proposed programme plan for 2026:

(a)	Office of Internal Oversight Services synthesis review of evaluation results for regional economic commissions – contributions to economic development;

(b)	Midterm assessment conducted by ESCWA of a project on climate resilience through regional cooperation for inclusive sustainable development.

22.14	In response to the results of the internal evaluation referenced above, the Commission will further enhance its interventions related to climate change by leveraging technological advances for enhanced capacity-building and knowledge dissemination and by strengthening and customizing stakeholders’ engagement and ownership utilization of outputs. In addition, the Commission will strengthen its assessment of the outcomes of its economic development activities, including through beneficiary surveys of training sessions and the monitoring of policies or action taken by policymakers.

22.15	In 2026, the Commission will conduct an internal evaluation of one of its six subprogrammes.

Programme of work

Subprogramme 1

Climate change and natural resource sustainability

Objective

22.16	The objective, to which this subprogramme contributes, is to advance climate action and integrated and sustainable policies in the areas of water, energy and food security.

Strategy

22.17	To contribute to the objective, the subprogramme will:

(a)	Deploy in-house expertise and collaborate with other United Nations entities and external experts to analyse and assess the impact of trends and challenges and disseminate knowledge products pertaining to issues such as transboundary and the integrated management of water resources; land degradation and biodiversity; extractive industries and energy transitions; equitable, resilient, inclusive and sustainable agrifood systems; the transition to circular economy approaches; sand and dust storms; climate adaptation and mitigation; and a means for assessing climate finance and data-driven knowledge platforms related to climate resilience;

(b)	Provide technical and policy advice and expertise to member States and strengthen capacities at the regional, national and sectoral levels to use evidence and tools to identify and operationalize solutions and mainstream considerations related to climate change, sustainable natural resource management and food security into national development plans and budgets, and identify opportunities for financing climate action and adaptation;

(c)	Convene intergovernmental platforms and technical bodies to facilitate cross-sectoral dialogue, consensus-building and peer-to-peer exchanges among policymakers, practitioners, experts, civil society and other development partners from within and outside the region to promote cooperation and coordination; foster consensus towards the development of national, transboundary and regional normative frameworks on the sustainable management of water, energy and land resources; facilitate the transition to circular economy approaches; and increase access to affordable, reliable, sustainable and modern energy;

(d)	Advocate with national Governments, regional intergovernmental bodies and relevant stakeholders, including through supporting the integrated, regional reporting on and monitoring of progress against specific Sustainable Development Goal targets; promote joint solutions and the harmonization of positions; and leverage partnerships in support of the implementation and financing of such commitments.

22.18	The above-mentioned work is expected to result in:

(a)	The adoption by member States of national policy frameworks and regional agreements related to climate action and the sustainable use and management of natural resources; reduced emissions; making the transition away from fossil fuels in energy systems in a just, orderly and equitable manner; resilient food systems supported by sustainable agriculture; and improved climate resilience;

(b)	Strengthened cooperation on issues outlined in paragraph 22.17 above, supported by inclusive networks and participatory coordination mechanisms.

Programme performance in 2024

Member States are better equipped to prepare the next round of nationally determined contributions for climate action

22.19	The next round of nationally determined contributions under the Paris Agreement are due in 2025. The subprogramme provided member States with technical assistance on the structure of their climate finance flows, training on adaptation costing, tools for reducing risks in the deployment of renewable energy and tailored data sets to inform climate action plans. During 2024, best practices for mainstreaming water, energy and food security into nationally determined contributions were shared during five regional forums convened or co-convened by ESCWA. The aim was to empower member States to broaden sector and stakeholder engagement in nationally determined contribution preparation and to articulate evidence-based adaptation programmes alongside mitigation goals. By the end of 2024, three member States (Iraq, Lebanon and Tunisia) benefited from improved capacity and tailored knowledge products to prepare their next round of nationally determined contributions.

22.20	Progress towards the objective is presented in the performance measure below (see table 22.2).

Table 22.2

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) |
| --- | --- | --- |
| Eleven member States costed their nationally determined contribution climate finance needs | Member States have access to knowledge products on ways to better articulate their adaptation and mitigation commitments and the related climate finance envelope | Three member States (Iraq, Lebanon and Tunisia) enhanced their understanding and capacity to prepare their next round of nationally determined contributions |

Planned results for 2026

Result 1: sustainable transition to new and renewable sources of energy underpinned by a transformed extractive industries sector

Programme performance in 2024 and target for 2026

22.21	The subprogramme’s work contributed to advancing national dialogues in two member States (Jordan and Saudi Arabia) on the transformation of the extractive energy sector, which did not meet the planned target of member States formulating national policy frameworks in support of transforming the extractive energy sector with a view to making the transition to affordable, reliable, sustainable and modern energy systems. The target was not met owing to liquidity-related constraints, which resulted in the lack of sufficient and dedicated resources for activities such as the organization of consultations at the national level and the production of national case studies.

22.22	Progress towards the objective and the target for 2026 are presented in the performance measure below (see table 22.3).

Table 22.3

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| Member States have access to information on extractive industries in the Arab region | Member States gained access to a suite of knowledge products and evidence on the role of minerals and raw materials in supporting the energy transition in the Arab region | Two member States (Jordan and Saudi Arabia) embarked on national dialogues on transforming the extractive energy sector towards affordable, reliable, sustainable and modern energy systems | Two member States implement policy recommendations and best practices for sustainable production of critical raw materials | One additional member State commences a national dialogue on transforming the extractive energy sector towards affordable, reliable, sustainable and modern energy systems |
| Strategic framework and road map for enabling just, inclusive, equitable and secure transition of the energy sector, based on the circular carbon economy framework, is developed for one member State (Kuwait) | States exchanged expertise and good practice, and coordinated national actions at the regional level through the regional expert group on extractive industries as well as dedicated platform at the Middle East and North Africa Climate Week 2023 |  |  |  |

Result 2: transitioning to sustainable food systems

Programme performance in 2024 and target for 2026

22.23	The subprogramme’s work contributed to two member States (Jordan and Lebanon) having assessed their national food systems, which exceeded the planned target of one member State.

22.24	Progress towards the objective and the target for 2026 are presented in the performance measure below (see table 22.4).

Table 22.4

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| – | Member States have access to regional tool for assessing food security | Two member States (Jordan and Lebanon) assessed their national food systems | One member State develops a framework for making the transition to sustainable food systems | One additional member State develops a framework for making the transition to sustainable food systems |

Result 3: member States identify joint priority action to combat sand and dust storms

Proposed programme plan for 2026

22.25	Sand and dust storms are an urgent transboundary challenge in Western Asia owing to climate change, land degradation and water scarcity. The subprogramme enhanced the capacity of member States to monitor and mitigate sand and dust storms, including through training, by making available geospatial mapping tools and assessments of the projected change in their frequency and intensity and by fostering knowledge exchange through the United Nations Coalition on Combating Sand and Dust Storms.

Lessons learned and planned change

22.26	The lesson for the subprogramme was that the transboundary nature of sand and dust storms required coordinated response measures at the intraregional and interregional levels. In applying the lesson, the subprogramme will conduct policy dialogues in collaboration with the Economic and Social Commission for Asia and the Pacific that will coincide with the launch of the United Nations Decade on Combating Sand and Dust Storms (2025–2034). This will foster common understanding among member States in Western and Central Asia to inform the joint identification of priority interventions aimed at enhancing preparedness and collaborative planning to mitigate sand and dust storms.

22.27	Expected progress towards the objective is presented in the performance measure below (table 22.5).

Table 22.5

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| – | – | Member States have access to geospatial tools for enhanced analysis of sand and dust storms | Member States have access to interregional dialogues on sand and dust storms | Member States identify joint priority action for sand and dust storm management in Western Asia and neighbouring areas |

Deliverables

22.28	Table 22.6 lists all deliverables of the subprogramme.

Table 22.6

Subprogramme 1: deliverables for the period 2024–2026, by category and subcategory

| Category and subcategory | 2024 planned | 2024 actual | 2025 planned | 2026 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Parliamentary documentation (number of documents) | – | – | 12 | – |
| 1. Committee on Energy | – | – | 6 | – |
| 2. Committee on Water Resources | – | – | 6 | – |
| Substantive services for meetings (number of three-hour meetings) | 30 | 29 | 42 | 28 |
| 3. Committee on Water Resources | – | – | 4 | – |
| 4. Committee on Energy and its Expert Group on Extractive Industries | – | – | 5 | – |
| 5. Committee on Water Resources and the Committee on Energy (joint) | – | – | 1 | – |
| 6. Executive Bureau of the Arab Ministerial Council for Electricity and its committees of experts on electricity and on renewable energy and energy efficiency | 6 | 6 | 6 | 6 |
| 7. Arab Ministerial Water Council and its Technical, Scientific and Advisory Committee | 6 | 6 | 6 | 6 |
| 8. Joint Ministerial Council for Water and Agriculture and its High-level Joint Technical Committee | – | – | 2 | – |
| 9. Arab Council of Ministers Responsible for Meteorology and Climate and its Permanent Committee for Meteorology, the Sub-Committee on Weather and Climate Risk Information Management and the Arab Climate Outlook Forum | 10 | 9 | 10 | 8 |
| 10. Council of Arab Ministers Responsible for the Environment and its Technical Committee | 8 | 8 | 8 | 8 |
| B. Generation and transfer of knowledge |  |  |  |  |
| Field and technical cooperation projects (number of projects) | 5 | 5 | 9 | 7 |
| 11. Climate resilience through regional cooperation for inclusive sustainable development | 1 | 1 | 1 | 1 |
| 12. Arab Centre for Climate Change Policies | 1 | 1 | 1 | 1 |
| 13. Centre for Advancing Emissions Reduction | 1 | – | 1 | 1 |
| 14. Regional Initiative for the Assessment of the Impact of Climate Change on Water Resources and Socio-Economic Vulnerability in the Arab Region (RICCAR) | 1 | 1 | 1 | 1 |
| 15. Arab Integrated Water Resources Management Network (AWARENET) | 1 | 1 | 1 | 1 |
| 16. Increasing the resilience of both displaced persons and host communities to climate change-related water challenges in Jordan and Lebanon | – | – | 1 | – |
| 17. Water scarcity initiative (climate change and groundwater) | – | – | 1 | 1 |
| 18. Mashreq Waters Knowledge Series | – | 1 | 1 | – |
| 19. Regional Initiative for Promoting Small-Scale Renewable Energy Applications in Rural Areas of the Arab Region (REGEND) | – | – | 1 | 1 |
| Seminar, workshops and training events (number of days) | – | 5 | 7 | 8 |
| 20. Seminars and workshops on topics related to climate change and sustainable natural resource management | – | 5 | 7 | 8 |
| Publications (number of publications) | 1 | 1 | 2 | 2 |
| 21. On topics related to climate action and sustainable natural resource management | 1 | 1 | 2 | 2 |
| Technical materials (number of materials) | 8 | 7 | 8 | 8 |
| 22. On topics related to climate action and sustainable natural resource management | 8 | 7 | 8 | 8 |
| C. Substantive deliverables |  |  |  |  |
| Consultation, advice and advocacy: expert groups on environment; water (security) and groundwater; energy; agriculture, food security, sustainable consumption and production, and circular economy approaches; and climate change, energy management and extractive industries. |  |  |  |  |
| Databases and substantive digital materials: groundwater knowledge platform; and e-learning on food systems monitoring framework, on climate change and on REGEND. |  |  |  |  |
| D. Communication deliverables |  |  |  |  |
| Outreach programmes, special events and information materials: briefs, fact sheets and booklets on topics identified in paragraph 22.17 (a) of the present report; side events at major meetings; global and regional events; and webinars. |  |  |  |  |

Subprogramme 2

Gender justice, population and inclusive development

Objective

22.29	The objective, to which this subprogramme contributes, is to achieve equitable and inclusive social development and reduced inequality, poverty and unemployment in line with the principle of leaving no one behind.

Strategy

22.30	To contribute to the objective, the subprogramme will:

(a)	Develop knowledge products and policy options and solutions, underpinned by the analysis of trends and challenges, international norms and regional perspectives on a wide range of issues pertaining to social inclusion and protection; social and gender justice; poverty reduction; labour market needs; migration; and the socioeconomic participation and empowerment of women, young people, older persons and persons with disabilities, especially those in vulnerable situations;

(b)	Support mandated reviews against global commitments and agreements; provide technical and policy advice; and strengthen national capacities to assess existing policy and legislative frameworks, to identify and operationalize viable legislation and solutions and to mainstream the reduction in inequalities and equal participation, protection and specific needs of those in vulnerable situations into national development plans and budgets;

(c)	Enhance existing and develop new methodologies, regional public goods and interactive tools for simulation and analysis of policy options and their impact on inclusive development trajectories;

(d)	Engage member States and development stakeholders in dialogue to advocate for the adoption of policy solutions and to forge consensus on issues outlined in paragraph 22.30 (a) above, while promoting South-South (intraregional and interregional) collaboration and peer learning.

22.31	The above-mentioned work is expected to result in:

(a)	National policy frameworks and strategies adopted by member States to address structural inequalities and promote social justice and greater social inclusion and the socioeconomic empowerment and participation of women, young people, older persons, persons with disabilities and migrants, especially those in vulnerable situations;

(b)	Enhanced coverage of the peoples of the region, in particular persons in vulnerable situations, through social protection and poverty eradication programmes and their improved access to decent and equitable employment opportunities.

Programme performance in 2024

Reaffirmed commitment to the Beijing Declaration and Platform for Action

22.32	Periodic reviews of the Beijing Declaration and Platform for Action allow countries to measure progress against commitments and to reflect on challenges and opportunities that affect full implementation. The subprogramme encouraged all Arab member States to engage in the current iteration of the review, which marked the thirtieth anniversary of the adoption of the Beijing Declaration and Platform for Action.

22.33	The subprogramme provided technical expertise and capacity-building support to 10 of the 18 member States that conducted the review, including the facilitation of national-level consultations with lawmakers, civil society representatives, the private sector and academic institutions. During 2024, the subprogramme supported member States in finalizing their national reports and co-led, together with the League of Arab States and the United Nations Entity for Gender Equality and the Empowerment of Women (UN-Women), a regional-level review to identify key achievements and measures undertaken over the past five years to address challenges in implementing the 12 critical areas of the Beijing Declaration and Platform for Action. Furthermore, the subprogramme facilitated negotiations among member States, which led to the adoption of a regional declaration reaffirming their commitment to the Beijing Declaration and Platform for Action.

22.34	Progress towards the objective is presented in the performance measure below (see table 22.7).

Table 22.7

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) |
| --- | --- | --- |
| Member States identified five priority areas to accelerate the implementation of the Beijing Declaration and Platform for Action and improve the status of women in the Arab region | Enhanced understanding and capacities of Arab national women’s machineries to conduct national reviews | Reaffirmed commitment and enhanced capacity of all Arab member States for the full implementation of the Beijing Declaration and Platform for Action |

Planned results for 2026

Result 1: skills-focused approaches to boost access to employment opportunities

Programme performance in 2024 and target for 2026

22.35	The subprogramme’s work contributed to three academic institutions utilizing the Skills Monitor as part of their career-planning support to graduates and to two member States (Jordan and Qatar) adopting the ESCWA future of work initiative framework in using artificial intelligence to build more dynamic labour market policies, which did not meet the planned target of at least 10 academic institutions in the Arab region using the Skills Monitor as part of their career-planning support to graduates. The target was not met owing to a shift in the subprogramme’s focus from uptake by academic institutions to the development of national policy frameworks.

22.36	Progress towards the objective and the target for 2026 are presented in the performance measure below (see table 22.8).

Table 22.8

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| Working-age populations in four member States (Jordan, Kuwait, Lebanon and Qatar) were enabled to identify job opportunities based on their skills through artificial intelligence-based Skills Monitor portal | Policymakers in 11 member States gained access to evidence on factors affecting the job market (skill sets in demand, inclusiveness) | Three academic institutions (Lebanese American University, Petra University and Al-Quds University) utilized the Skills Monitor as part of their career-planning support to graduates | Two member States develop policy frameworks aimed at boosting access to the labour market | One member State implements labour market policy to enhance market skills needed for the future of work |
|  |  | Two member States (Jordan and Qatar) adopted the ESCWA future of work initiative framework |  |  |

Result 2: member States adopt multidimensional approach to poverty reduction

Programme performance in 2024 and target for 2026

22.37	The subprogramme’s work contributed to two member States (Egypt and Jordan) utilizing a nationalized multidimensional poverty index and assist tool to assess drivers of poverty, including inequalities and exclusion, which met the planned target.

22.38	Progress towards the objective and the target for 2026 are presented in the performance measure below (see table 22.9).

Table 22.9

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| One member State (State of Palestine) piloted a nationalized multidimensional poverty index | Two member States (Iraq and Somalia) adopted a nationalized multidimensional poverty index as a poverty analysis tool | Two member States (Egypt and Jordan) utilized a nationalized multidimensional poverty index and assist tool to assess drivers of poverty, including inequalities and exclusion | Two member States develop policy frameworks and/or strategies for the eradication of poverty | One additional member State develops policy framework and/or strategy for the eradication of poverty |

Result 3: member States leverage machine learning to forecast budget needs for social assistance programming

Proposed programme plan for 2026

22.39	Financial allocations received by Governments of developing countries to establish social assistance programmes are often ad hoc, and the level of support is determined by donors on the basis of their relevant priorities and budget availability and not on government estimates of social assistance needs. The subprogramme conducted studies to assess the effectiveness and efficiency of current social protection systems and programmes, supported in part by machine learning-aided statistical analysis.

Lessons learned and planned change

22.40	The lesson for the subprogramme was that increased data availability and enhanced database interoperability in the region’s middle- and low-income countries provided fertile ground for developing and institutionalizing machine learning-based applications in support of ministries’ ability to forecast social assistance budget needs. In applying the lesson, the subprogramme will assess the feasibility of such applications, including data exchange and coding requirements. The subprogramme will also develop and institutionalize a tailored machine learning-based forecasting application for member States.

22.41	Expected progress towards the objective is presented in the performance measure below (see table 22.10).

Table 22.10

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| – | – | Machine learning-enabled general approach for the forecasting of budget needs for social assistance programmes developed | One member State has access to a prototype of a machine learning-enabled model for the forecasting of budget needs for social assistance programmes | One member State operationalizes social assistance budget forecasting models and dashboards |

Deliverables

22.42	Table 22.11 lists all deliverables of the subprogramme.

Table 22.11

Subprogramme 2: deliverables for the period 2024–2026, by category and subcategory

| Category and subcategory | 2024 planned | 2024 actual | 2025 planned | 2026 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Parliamentary documentation (number of documents) | – | 5 | 12 | 12 |
| 1. Committee on Women | – | 5 | 6 | 6 |
| 2. Committee on Social Development | – | – | 6 | 6 |
| Substantive services for meetings (number of three-hour meetings) | 1 | 8 | 9 | 9 |
| 3. Committee on Social Development | – | – | 2 | 2 |
| 4. Committee on Women | – | 4 | 4 | 4 |
| 5. Subcommittees on social protection, gender and the Sustainable Development Goals, and the intersessional group of experts on disability | 1 | 4 | 3 | 3 |
| B. Generation and transfer of knowledge |  |  |  |  |
| Field and technical cooperation projects (number of projects) | 2 | 5 | 4 | 2 |
| Projects on: |  |  |  |  |
| 6. Enhancing the employment of persons with disability | – | 1 | 1 | – |
| 7. Assessing skills and skills matching techniques | 1 | 1 | 1 | 1 |
| 8. Towards Beijing +30 review | – | 1 | 1 | – |
| 9. Strengthening social protection systems | – | 1 | 1 | 1 |
| 10. Women and peace and security: moving from plans to action | 1 | 1 | – | – |
| Seminars, workshops and training events (number of days) | 20 | 18 | 22 | 16 |
| 11. Social justice, including integrating social justice principles into public policies and programmes | 8 | 8 | 8 | 2 |
| 12. Gender justice and women’s empowerment | 4 | 4 | 4 | 4 |
| 13. Population development, ageing, disability and migration | 2 | 2 | 4 | 6 |
| 14. Multidimensional poverty and social protection | 6 | 4 | 6 | 4 |
| Publications (number of publications) | 2 | 2 | 3 | 2 |
| 15. On the realization of human rights for women; social protection; poverty; inequality; the future of work; and disability and migration | 2 | 2 | 3 | 2 |
| Technical materials (number of materials) | 22 | 20 | 20 | 22 |
| 16. On the realization of human rights for women; social protection; poverty; inequality; the future of work; and disability and migration | 22 | 20 | 20 | 22 |
| C. Substantive deliverables |  |  |  |  |
| Consultation, advice and advocacy: meetings of expert groups on advancement of the participation of women in decision-making; women’s economic empowerment; financial inclusion; social protection; poverty; inequality; informality and the labour market; the future of work; urban development; disability; migration; ageing; and young people. |  |  |  |  |
| Databases and substantive digital materials: social protection programme – rapid assessment framework; ESCWA Skills Monitor; gender justice portal; gender policy simulator platform; multidimensional poverty index; and policy simulation and optimization platform. |  |  |  |  |
| D. Communication deliverables |  |  |  |  |
| Outreach programmes, special events and information materials: campaign, promotional materials and closing ceremony for the 16 Days of Activism against Gender-based Violence; materials on equality in the Arab region; and advocacy campaigns on International Day of Older Persons and International Migrants Day. |  |  |  |  |
| External and media relations: commentaries on violence against women and on the economic empowerment of women. |  |  |  |  |

Subprogramme 3

Shared economic prosperity

Objective

22.43	The objective, to which this subprogramme contributes, is to achieve equitable economic growth, amplify regional interconnectedness and integration, and advance the effective implementation of the Addis Ababa Action Agenda of the Third International Conference on Financing for Development in support of the 2030 Agenda.

Strategy

22.44	To contribute to the objective, the subprogramme will:

(a)	Develop and provide knowledge products and evidence for policymaking related to trade, logistics and transport, including regional integration; the application of behavioural science in development, public policy monitoring and evaluation systems; economic diversification and macroeconomic stability; debt sustainability and fiscal policies as a means of enhancing investment in sustainable development priorities; and financing for development, including integrated national financing frameworks;

(b)	Enhance existing and develop new dynamic, data-driven policy simulation tools (anchored in artificial intelligence and machine learning approaches) pertaining to trade flows, taxation, debt optimization, debt swaps, social expenditure, the monitoring and evaluation of development plans and contextualized economic modelling, and promote the application of modern technologies to facilitate trade and logistics;

(c)	Make available to its member States policy advice and technical expertise and strengthen capacities to deploy behavioural insights and modelling and impact simulation tools in support of decision-making and policy development processes aimed at providing immediate, medium- and long-term solutions to national development challenges in the areas identified in paragraph 22.44 (a) above;

(d)	Promote collaboration, coordination and the exchange of good practice; and foster consensus on priorities and joint initiatives aimed at improving regional integration, facilitating trade, promoting innovative debt solutions and enhancing fiscal space and financing for sustainable development initiatives.

22.45	The above-mentioned work is expected to result in:

(a)	Evidence-backed development planning; member States adopting policy frameworks to address structural economic challenges; improved debt management and sustainability; enhanced equity, efficiency and effectiveness of public spending and budgeting, including on national development priorities; new trade opportunities and economic diversification, including enhanced operational environment for small and medium-sized enterprises; and the creation of fiscal space for social investment in basic social services and the achievement of sustainable development goals;

(b)	Increased contribution of small and medium-sized enterprises to national and regional economies and greater economic participation and empowerment of individuals, including those in vulnerable situations.

Programme performance in 2024

Tunisia develops a climate/Sustainable Development Goals debt swap programme

22.46	Amid the challenges of rising debt and debt servicing, the global economic slowdown, persistent trade deficits and climate change, financing for sustainable development and climate action are becoming increasingly difficult. Considering pressures on public budgets and financing gaps, mobilizing funding without adding more debt is a priority. The ESCWA climate/the Sustainable Development Goals debt swap initiative supports member States in developing programme-based debt swaps towards enhancing fiscal space to finance climate action and the Goals. Building on the previous achievements of the initiative, the subprogramme supported Tunisia in operationalizing an inter-agency task force mandated with the development of a climate/Goals debt swap programme, including a priority list of projects, for negotiation with creditors. The projects were to contribute to achieving nationally determined contribution priority action in areas such as water, energy and the environment, while addressing climate and socioeconomic vulnerabilities. Specifically, in 2024 the subprogramme promoted an inclusive, intersectoral platform approach and provided technical expertise and advice, including on the establishment of key performance indicators for impact assessments at the project and programme levels, which also facilitated the prioritization of projects.

22.47	Progress towards the objective is presented in the performance measure below (see table 22.12).

Table 22.12

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) |
| --- | --- | --- |
| One member State (Jordan) developed a climate/Sustainable Development Goals debt swap programme proposal | – | One member State (Tunisia) developed a climate/Sustainable Development Goals debt swap programme proposal |

Planned results for 2026

Result 1: contextualised economic modelling informs development of economic, social and trade policies

Programme performance in 2024 and target for 2026

22.48	The subprogramme’s work contributed to the upgrading of the existing computable general equilibrium models developed for two member States (Oman and United Arab Emirates), which did not meet the planned target of three additional member States using computable general equilibrium models. The target was not met owing to liquidity-related resource constraints, which impeded the carrying out of activities such as the production of related technical materials.

22.49	Progress towards the objective and the target for 2026 are presented in the performance measure below (see table 22.13).

Table 22.13

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| Two member States (Yemen and State of Palestine) used national computable general equilibrium models | Three additional member States (Mauritania, Oman and United Arab Emirates) used computable general equilibrium models | Two member States (Oman and United Arab Emirates) have access to upgraded computable general equilibrium models | Two additional member States use computable general equilibrium models | One additional member State uses the computable general equilibrium model |

Result 2: enhanced debt sustainability for increased investment in sustainable development priorities

Programme performance in 2024 and target for 2026

22.50	The subprogramme’s work contributed to two member States (Mauritania and Oman) having access and improved capacity to deploy the tool and recommendations to optimize debt and identify innovative and sustainable debt financing strategies, which met the planned target.

22.51	Progress towards the objective and the target for 2026 are presented in the performance measure below (see table 22.14).

Table 22.14

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| A regional network of debt management practitioners and experts was established | Member States gained access to regional and country-specific analyses on debt optimization and innovative debt solutions | Two member States (Mauritania and Oman) have access and improved capacity to deploy the tool and recommendations to optimize debt and identify innovative and sustainable debt financing strategies | Two member States develop innovative and sustainable debt financing strategies | One additional member State develops an innovative and sustainable debt financing strategy |

Result 3: member States reach bilateral trade agreements beyond the region

Proposed programme plan for 2026

22.52	External trade is one of the key factors that underpin sustainable economic development and diversification. Therefore, national frameworks governing it ought to align with these long-term objectives, which are crucial for achieving the Sustainable Development Goals. The subprogramme developed the Arab trade simulator interface to support evidence-based decision-making regarding trade opportunities as a first step to developing tailored national interfaces.

Lessons learned and planned change

22.53	The lesson learned for the subprogramme was that more tailored analyses for individual member States was needed to reflect specificities of domestic economic models and priorities against the backdrop of global economic and trade indicators. In applying the lesson, the subprogramme will develop national global economy-wide trade simulator interfaces, customized for each member State, which will empower users in testing and evaluating alternative trade policies and enabling preconditions at the national, regional and global levels. The subprogramme will also develop the skills and capacities of civil servants to enable them to better negotiate trade offers.

22.54	Expected progress towards the objective is presented in the performance measure below (see table 22.15).

Table 22.15

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| – | – | Arab trade simulator interface is available to member States | At least two member States have access to national global economy-wide trade simulator interface platforms | One member State applies the global economy-wide trade simulator interface to develop a bilateral trade agreement |

Deliverables

22.55	Table 22.16 lists all deliverables of the subprogramme.

Table 22.16

Subprogramme 3: deliverables for 2024–2026, by category and subcategory

| Category and subcategory | 2024 planned | 2024 actual | 2025 planned | 2026 planned |  |
| --- | --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |  |
| Parliamentary documentation (number of documents) | 12 | 6 | 12 | 12 |  |
| 1. Committee on Trade Policies | 6 | – | – | 6 |  |
| 2. Committee on Transport and Logistics | 6 | 6 | 6 | 6 |  |
| 3. Committee on Financing for Development | – | – | 6 | – |  |
| Substantive services for meetings (number of three-hour meetings) | 8 | 12 | 8 | 8 |  |
| 4. Committee on Trade Policies | 4 | – | – | 4 |  |
| 5. Committee on Transport and Logistics | 4 | 8 | 4 | 4 |  |
| 6. Committee on Financing for Development | – | 4 | 4 | – |  |
| B. Generation and transfer of knowledge |  |  |  |  |  |
| Field and technical cooperation projects (number of projects) | 2 | 2 | 1 | 2 |  |
| 7. Arab integrated road safety observatory | 1 | 1 | 1 | 1 |  |
| 8. National agenda for the future of Syria – phases II and III | 1 | 1 | – | – |  |
| 9. Climate/the Sustainable Development Goals debt swap | – | – | – | 1 |  |
| Seminars, workshops and training events (number of days) | 8 | 8 | 8 | 8 |
| 10. Seminars and workshops on transport and logistics, economic modelling, and use of policy simulators | 8 | 8 | 8 | 8 |
| Publications (number of publications) | 2 | 2 | 1 | 1 |  |
| 11. On issues relating to economic development | 2 | 2 | 1 | 1 |  |
| Technical materials (number of materials) | 22 | 17 | 20 | 17 |  |
| 12. On public finance and inclusive fiscal policy, including in low- and middle-income countries; trade and industrial policy; trade facilitation; transport connectivity and logistics; the productive capacity of Arab least developed countries; illicit financial flows; financing for development; and climate action | 22 | 17 | 20 | 17 |  |
| C. Substantive deliverables |  |  |  |  |  |
| Consultation, advice and advocacy: expert groups on public finance; debt and innovative financing instruments; financing for development; trade policy and facilitation; transport connectivity; dynamic computable general equilibrium economic modelling; illicit financial flows and strategic advice to the United Nations Road Safety Fund Steering Committee. |  |  |  |  |  |
| Databases and substantive digital materials: Arab Trade Gateway; financing for development gateway; integrated budget intelligence toolkit; dynamic financing for development simulator; social expenditure monitor; debt optimization portal; macro-fiscal modelling and forecasting tool; and Sustainable Development Goal costing calculator for the Arab region. |  |  |  |  |  |
| D. Communication deliverables |  |  |  |  |  |
| Outreach programmes, special events and information materials: side event at the Arab Forum for Sustainable Development. |  |  |  |  |  |

Subprogramme 4

Statistics, the information society and technology

Objective

22.56	The objective, to which this subprogramme contributes, is to strengthen the development of official statistical frameworks, improve the quality and availability of statistics and advance the information society by accelerating the integration of technology and innovation for sustainable development in the Arab region.

Strategy

22.57	To contribute to the objective, the subprogramme will:

(a)	Develop methodologies and tools to enhance the capacities of national statistical systems to implement and adapt to evolving international statistical standards, methodologies and best practices, and promote the integration of innovative data sources and geostatistical information;

(b)	In line with global and regional processes, such as the Global Digital Compact and WSIS+20, develop knowledge products, models, toolkits and platforms and enhance the capacity of policymakers and practitioners in member States to produce evidence and, on that basis, develop digital policy frameworks and strategies aimed at enhancing digital infrastructure, digital transformation, digital economy, digital government and e-accessibility, in support of the implementation of the 2030 Agenda;

(c)	Enhance national capacities to produce and utilize quality statistics and data for evidence-based policymaking and provide technical support for the adoption of policy frameworks, statistical methodologies and strategies to harness emerging technologies and innovative solution for monitoring and reporting on sustainable development indicators, in line with national plans and priorities, and increase the value created from statistics, geospatial-enabled data, digitization and emerging technologies;

(d)	Convene intergovernmental and technical, multi-stakeholder forums to foster consensus and facilitate dialogue and exchanges, with the aim of promoting cooperation, partnerships and coordination and incentivizing investment in advancing both digital development and transformation and the production of quality statistics and data.

22.58	The above-mentioned work is expected to result in:

(a)	An enhanced value chain of timely, accessible, interoperable and integrated data from diverse sources, including geolocated and disaggregated data, that is compliant with international statistical standards;

(b)	Member States developing, adopting and implementing enhanced policy frameworks pertaining to digital and emerging technologies, as a means of accelerating the achievement of the Sustainable Development Goals.

Programme performance in 2024

Djibouti and Jordan apply modernized approaches to censuses

22.59	Statistical information obtained through censuses remains a core reference for the analysis and interpretation of evidence, and the accuracy, efficiency and timeliness of the data that it yields is therefore critical. During 2024, the subprogramme provided member States with technical expertise and advice on the design and conduct of national censuses, including the deployment of modern technology and the digitization of data collection (Djibouti) and the piloting of a multi-source methodology that would enable a register-based census (Jordan). Concurrently, the subprogramme organized study tours, which promoted peer-to-peer exchanges between Djibouti and Egypt and between Jordan and Oman, and resulted in enhanced capacities of national statistical offices in Djibouti and Jordan to apply modernized approaches to data collection, further enhancing quality and compliance with international standards. Furthermore, Egypt’s Central Agency for Public Mobilization and Statistics supported the Institut de la statistique de Djibouti by providing 1,400 tablets for a digitized census.

22.60	Progress towards the objective is presented in the performance measure below (see table 22.17).

Table 22.17

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) |
| --- | --- | --- |
| Two member States (Jordan and Oman) engaged in a peer-to-peer exchange of best practices on multi-source census methodology | One member State (Djibouti) benefited from the support of another (Egypt) in the development of a digitized approach to censuses | One member State (Djibouti) conducted its first-ever digital census |
|  |  | One member State (Jordan) piloted a multi-source (register-based) census methodology |

Planned results for 2026

Result 1: Arab policymakers gain access to on-demand, reliable evidence enabled by artificial intelligence and geospatial capacities

Programme performance in 2024 and target for 2026

22.61	The subprogramme’s work contributed to four member States (Egypt, Jordan, Qatar and Tunisia) generating evidence and simulating policy options and related impacts through five artificial intelligence and geospatial-enabled interactive tools, which met the planned target.

22.62	Progress towards the objective and the target for 2026 are presented in the performance measure below (see table 22.18).

Table 22.18

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| Member States gained access to additional national, regional and global (statistical and non-statistical) data sets | Member States gained access to centralized, regional data management and analytics platform (United Nations Arab Region Data and Policy Support hub) | Four member States (Egypt, Jordan, Qatar and Tunisia) generated evidence and simulated policy options and related impacts through five artificial intelligence- and geospatial-enabled interactive tools | Member States have access to national data and policy dashboards through a one-stop shop for evidence-based policymaking | Three additional member States successfully integrate at least two of the artificial intelligence and data-driven tools into their policy development processes, resulting in the generation of actionable policy insights |

Result 2: geostatistical evidence enhances decision-making and development planning in the Arab region

Programme performance in 2024 and target for 2026

22.63	The subprogramme’s work contributed to all member States having access to an additional 12 layers of geostatistical information, in particular those related to climate and the environment, which met the planned target.

22.64	Progress towards the objective and the target for 2026 are presented in the performance measure below (see table 22.19).

Table 22.19

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| Geostatistical laboratory for the Arab region was established | All member States gained access to an initial 12 layers of geostatistical information | All member States have access to an additional 12 layers of geostatistical information, in particular those related to climate and the environment | Two national statistical offices in the Arab region produce geostatistical data sets | One member State utilizes the geostatistical atlas of the Arab world to generate evidence for decision-making or policy development |
|  | Two member States (Jordan and Lebanon) initiated pilot projects to enhance their statistical data sets with geospatial information |  |  |  |

Result 3: Arab member States, including least developed countries, produce external trade statistics

Proposed programme plan for 2026

22.65	The availability of trade statistics is essential for effective economic policymaking. However, such statistics remain unavailable for 6 of 21 ESCWA member States, including 3 Arab least developed countries. The subprogramme has been estimating trade data for these countries to address gaps in the external trade statistics database for the Arab region.

Lessons learned and planned change

22.66	The lesson for the subprogramme was twofold: (a) the data estimates, while used regionally, could not be incorporated into the global United Nations Comtrade Database to close the data gap for better-informed decision-making; and (b) there were risks related to the sustainability of the continued replacement of official statistics by estimates. In applying the lesson, the subprogramme will collaborate with member States to enhance their capacity in internationally agreed frameworks for the compilation of and reporting on international trade statistics, alternative methodologies and programming skills. In addition, the peer-to-peer exchange of knowledge will be facilitated through study tours, to further empower the targeted countries to produce trade statistics independently.

22.67	Expected progress towards the objective is presented in the performance measure below (see table 22.20).

Table 22.20

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| – | – | Estimates for trade statistics are available to Iraq, Libya, Somalia, the Sudan, the Syrian Arab Republic and Yemen | Enhanced capacity of at least three member States, including at least one Arab least developed country, in producing trade statistics | At least one least developed Arab member State produces trade statistics |

Deliverables

22.68	Table 22.21 lists all deliverables of the subprogramme.

Table 22.21

Subprogramme 4: deliverables for 2024–2026, by category and subcategory

| Category and subcategory | 2024 planned | 2024 actual | 2025 planned | 2026 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Parliamentary documentation (number of documents) | 10 | 14 | – | 10 |
| 1. Committee on Technology for Development | 4 | 8 | – | 4 |
| 2. Statistical Committee | 6 | 6 | – | 6 |
| Substantive services for meetings (number of three-hour meetings) | 27 | 18 | 12 | 20 |
| 3. Committee on Technology for Development | 4 | – | – | 4 |
| 4. Statistical Committee | 4 | 4 | – | 4 |
| 5. ESCWA Technology Centre Advisory Board and Technical Committee | 3 | – | 2 | – |
| 6. The Bureau of the Statistical Committee | 2 | 2 | – | – |
| 7. Standing working groups of the Statistical Committee on economic statistics, demographic and social statistics and disability in the Sustainable Development Goals | 6 | 6 | 4 | 4 |
| 8. Task force on Sustainable Development Goals data of the Regional Collaborative Platform for Arab States | 2 | 2 | – | 2 |
| 9. Regional Committee of United Nations Global Geospatial Information Management for the Arab States | 2 | – | 2 | 2 |
| 10. League of Arab States on Internet governance; automated digital network systems; the digital economy; innovation policies; enhanced information and communications technology (ICT) cooperation; ICT strategy; science, technology and innovation; and ICT for the Sustainable Development Goals | 4 | 4 | 4 | 4 |
| B. Generation and transfer of knowledge |  |  |  |  |
| Field and technical cooperation projects (number of projects) | 1 | 1 | 1 | 1 |
| 11. ESCWA Technology Centre | 1 | 1 | 1 | 1 |
| Seminars, workshops and training events (number of days) | 24 | 21 | 24 | 22 |
| 12. Sustainable Development Goals statistics, including gender and disability statistics; big data and open data; Sustainable Development Goals measuring and reporting; digital inclusion; digital transformation; emerging technologies, digital government, digital economy, e-commerce; and entrepreneurship | 24 | 21 | 24 | 22 |
| Publications (number of publications) | 2 | 2 | 3 | 2 |
| 13. On statistics and indicators; Sustainable Development Goals data; non-traditional data sources; national accounts; purchasing power parity; monitoring of and follow-up on the 2030 Agenda; digital development; and technology and innovation for sustainable development | 2 | 2 | 3 | 2 |
| Technical materials (number of materials) | 6 | 6 | 6 | 8 |
| 14. On statistics and indicators; Sustainable Development Goals data; non-traditional data sources; national accounts; purchasing power parity; monitoring of and follow-up on the 2030 Agenda; digital development; and technology and innovation for sustainable development | 6 | 6 | 6 | 8 |
| C. Substantive deliverables |  |  |  |  |
| Consultation, advice and advocacy: meetings of experts on digital development; regulation and legislation to promote the information society; Internet governance; frontier technologies; entrepreneurship; technology transfer; and innovation. |  |  |  |  |
| Databases and substantive digital materials: ESCWA data ecosystem; Arab Sustainable Development Goals gateway; external trade data platform; and purchasing power parities convertor for the Arab region. |  |  |  |  |
| D. Communication deliverables |  |  |  |  |
| Outreach programmes, special events and information materials: annual statistics newsletter; and technology bulletin. |  |  |  |  |

Subprogramme 5

2030 Agenda and SDG coordination

Objective

22.69	The objective, to which this subprogramme contributes, is to accelerate progress towards sustainable development in the Arab region in line with the 2030 Agenda and to advance intraregional collaboration and a multi-stakeholder approach to key regional and subregional sustainable development issues.

Strategy

22.70	To contribute to the objective, the subprogramme will:

(a)	Advocate with a diverse set of stakeholders, including policymakers, the private sector, academic institutions and civil societies, for principled action towards the implementation of the 2030 Agenda, in particular in line with the commitment to “leave no one behind” and a people-centred approach to development, and leverage a broad range of partnerships, including with the private sector and financial institutions, intergovernmental and non-governmental organizations, civil society, and academic institutions and think tanks, to promote a whole-of-government and whole-of-society approach;

(b)	Develop and disseminate knowledge products underpinned by the analysis of member States’ progress towards the implementation of the 2030 Agenda and its principles, including gaps in policy frameworks, and promote transformative development solutions for accelerating inclusive, sustainable development in the region;

(c)	Convene and ensure ongoing support for and follow-up on various platforms, in connection with the Arab Forum for Sustainable Development, to facilitate multi-stakeholder engagement and dialogue and peer-to-peer exchanges; to foster consensus on sustainable development priorities and action; to promote subregional, interregional and intraregional (South-South) and triangular collaboration and coordination; and to support cross-sectoral cooperation and alignment of national development priorities and plans with both the 2030 Agenda and resources available for their implementation;

(d)	Enhance capacities to conduct integrated monitoring and reporting, at the local, national and regional levels, of the progress against specific Sustainable Development Goal targets, including through the building of national and institutional capacity to conduct voluntary national reviews and the identification of policy gaps; identify and disseminate innovative policy solutions and recommendations; ensure that the region’s perspective is reflected through a global lens; and foster cross-sectoral coordination of the Commission’s support to member States’ efforts to achieve the Sustainable Development Goals.

22.71	The above-mentioned work is expected to result in:

(a)	Enhanced commitment of policymakers and practitioners, regional intergovernmental organizations, the private sector, including financial institutions, academia and think tanks, and civil society organizations in the Arab region to the principles of the 2030 Agenda;

(b)	The adoption by member States and development stakeholders of a more participatory, whole-of-government and whole-of-society approach to the implementation of and follow-up on Sustainable Development Goal priorities and related action;

(c)	Improved utilization by member States and development stakeholders of available dialogue and advocacy platforms as a means of promoting consensus, peer-to-peer learning and coordination at the national, subregional, intraregional, interregional and global levels; and mobilizing sustained, targeted financing for an accelerated implementation of the 2030 Agenda;

(d)	Improved capacity of policymakers and other stakeholders to identify policy gaps and related policy opportunities and solutions and take action to advance the achievement of the Sustainable Development Goals.

Programme performance in 2024

Strengthened local governance for development through the first iteration of the Arab Mayors Academy

22.72	The Arab region faces a critical gap in capacity-building for local authorities, limiting their ability to align with global agendas such as the 2030 Agenda, the New Urban Agenda and the Pact for the Future. The subprogramme partnered with the United Nations Human Settlements Programme (UN-Habitat) and United Cities and Local Governments to launch the Arab Mayors Academy, the first regional learning initiative, collaboratively designed with local authorities. The initiative was set up as a network of Arab city leaders and global development stakeholders to empower local governance and catalyse resilience and sustainability in cities throughout the region. In 2024, the first iteration of the Academy gathered experts from more than 20 global entities, including international organizations, non-governmental organizations, academia and the private sector, to offer 11 senior city officials a hybrid curriculum, primarily in Arabic, focusing on the localization of the Sustainable Development Goals, emergency preparedness, smart sustainable cities, quality of life in cities, climate resilience, urban financing, partnerships and diplomacy, among others. Moreover, the online discussions component was open to the broader public, reaching more than 80 representatives of local authorities on each occasion.

22.73	Progress towards the objective is presented in the performance measure below (see table 22.22).

Table 22.22

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) |
| --- | --- | --- |
| – | – | Eleven senior city officials graduate from the first iteration of the Arab Mayors Academy and are better equipped to localize the Sustainable Development Goals |

Planned results for 2026

Result 1: university graduates play part in a whole-of-society, principled approach to achieving the Sustainable Development Goals

Programme performance in 2024 and target for 2026

22.74	The subprogramme’s work contributed to two academic institutions in the Arab region incorporating shared principles and commitments of the Sustainable Development Goals into their curricula, which met the planned target.

22.75	Progress towards the objective and the target for 2026 are presented in the performance measure below (see table 22.23).

Table 22.23

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| Sustainable Development Goals-focused research by Arab academic institutions contributes to regional and national dialogues on implementing the 2030 Agenda | One university faculty in a member State (the Artificial Intelligence, Data Science and Computing Hub at the American University of Beirut) committed to incorporating shared principles and commitments of the Goals into its programmes | Two academic institutions in the Arab region (Ali Bin Abi Taleb and Al Kawthar schools in Lebanon) incorporated shared principles and commitments of the Goals into their curricula | Academic institutions in at least four member States use The ESCWA Stories to promote principles of the 2030 Agenda among young people | Academic institutions in two member States benefit from awareness-raising by private sector entities on climate action and cybersecurity |

Result 2: increased private sector investment in regional and national sustainable development priorities

Programme performance in 2024 and target for 2026

22.76	The subprogramme’s work contributed to member States and private sector leaders engaging in a regional dialogue on support for and financing of Sustainable Development Goal priorities, which met the planned target.

22.77	Progress towards the objective and the target for 2026 are presented in the performance measure below (see table 22.24).

Table 22.24

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| – | The Union of Arab Banks committed to mobilizing up to $1 trillion in Sustainable Development Goal-related financing by 2030 | Member States and private sector leaders engaged in a regional dialogue on support for and financing of Goal priorities | One member State and private sector representatives jointly agree on a set of sustainable development priorities for private sector contributions | One additional member State and private sector representatives jointly agree on a set of sustainable development priorities for private sector contributions |

Result 3: member States identify and address policy gaps linked to the implementation of the 2030 Agenda

Proposed programme plan for 2026

22.78	Arab countries’ modest progress on achieving the Sustainable Development Goals highlights the need to evaluate the adequacy of national policies and capacities for policy assessment and reform. The subprogramme strengthened the regional knowledge base on Goals-related policy frameworks, including by analysing regional trends and gaps in design and implementation, and provided a platform for knowledge exchange on the 2030 Agenda follow-up and review.

Lessons learned and planned change

22.79	The lesson for the subprogramme was that, to drive the policy change necessary to accelerate progress in the achievement of the Sustainable Development Goals, the subprogramme needed to provide capacity-building support for strengthening the analytical quality of national follow-up and review processes. In applying the lesson, the subprogramme will enhance the skills and capacities of Goals coordination teams in member States to lead cross-sectoral policy assessments and identify national Goals policy gaps and solutions. The subprogramme will also restructure its dialogue platform to ensure the more inclusive participation of relevant stakeholders and improve their access to global and regional good practices in the area.

22.80	Expected progress towards the objective is presented in the performance measure below (see table 22.25).

Table 22.25

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| – | – | Member States have access to regional Sustainable Development Goal policy trends, opportunities and gaps, and commensurate policy solutions are proposed | Member States have access to regional modules and frameworks on public policy assessments | One member State identifies a national Goals policy gap and related policy solution(s) |

Deliverables

22.81	Table 22.26 lists all deliverables of the subprogramme.

Table 22.26

Subprogramme 5: deliverables for 2024–2026, by category and subcategory

| Category and subcategory | 2024 planned | 2024 actual | 2025 planned | 2026 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Substantive services for meetings (number of three-hour meetings) | 8 | 9 | 8 | 8 |
| 1. Meetings of the Arab Forum for Sustainable Development | 8 | 9 | 8 | 8 |
| B. Generation and transfer of knowledge |  |  |  |  |
| Field and technical cooperation projects (number of projects) | – | 1 | 1 | 1 |
| 2. ESCWA Stories | – | 1 | 1 | 1 |
| Seminars, workshops and training events (number of days) | 3 | 3 | 3 | 3 |
| 3. Voluntary national review workshops | 3 | 3 | 3 | 3 |
| Publications (number of publications) | 1 | 1 | – | – |
| 4. Arab sustainable development report | 1 | 1 | – | – |
| Technical materials (number of materials) | 3 | 3 | 3 | 3 |
| 5. Annual Sustainable Development Goals review | 1 | 1 | 1 | 1 |
| 6. On sustainable development | 2 | 2 | 2 | 2 |
| C. Substantive deliverables |  |  |  |  |
| Consultation, advice and advocacy: consultation with the task force of the Arab Forum for Sustainable Development; consultations on financial inclusion; advice to global and regional events on the 2030 Agenda; advice to the community of practice on voluntary national reviews; and promoting the Sustainable Development Goals among young people and educators. |  |  |  |  |
| Databases and substantive digital materials: SDG Knowledge and Learning platform. |  |  |  |  |

Subprogramme 6

Governance and conflict prevention

Objective

22.82	The objective, to which this subprogramme contributes, is to advance just, peaceful and inclusive societies, especially for people living under occupation or in conflict or post-conflict settings; to improve governance and strengthen effective, efficient and accountable public institutions; and to enhance service delivery.

Strategy

22.83	To contribute to the objective, the subprogramme will:

(a)	Generate and make available evidence-based policy analysis and recommendations to member States and relevant stakeholders, grounded in the principle of a human development approach, with a focus on mitigating the impact of conflict and occupation on the capacity to achieve the Sustainable Development Goals, facilitating national recovery and improving governance and institutional capacities to deliver basic services and respond to shocks; strengthening regional cooperation on governance and public administration; and boosting the competitiveness of the business environment, including consumer protection mechanisms;

(b)	Provide technical expertise, methodologies and tools while enhancing capacities to identify and operationalize immediate, medium- and long-term solutions, aimed at pre-emptively addressing emerging socioeconomic, environmental and governance challenges and conflicts; enhancing prevention, recovery and development planning; improving transparency and accessibility and the efficiency of State-run services; and reinforcing competition policies and consumer protection mechanisms that uphold fair market practices and improve transparency;

(c)	Foster South-South (intraregional and interregional) and triangular cooperation and build consensus on the priorities and action required to minimize the impact of conflict and any sudden shocks, inter alia, on the ability of member States to advance their national development agendas;

(d)	Support the five Arab least developed countries, within the framework of the Doha Programme of Action (2022–2031), by strengthening their institutional capacities for implementing the 2030 Agenda and graduating from the least developed countries category;

(e)	Enhance the capabilities of Palestinian institutions to mitigate the adverse effects of the Israeli occupation on development, including by supporting national recovery efforts and capacities in the Occupied Palestinian Territory and reducing the asymmetric dependency of its economy.

22.84	The above-mentioned work is expected to result in:

(a)	Improved understanding and prevention of development challenges associated with sudden shocks, including conflict, and effective mitigation of their impact on national development and recovery trajectories;

(b)	More effective public institutions, in particular in the five Arab least developed countries, with enhanced capabilities to deliver basic services in a transparent, accessible and inclusive way;

(c)	Operationalization of a contextualized, people-centred approach to development planning and policy formulation;

(d)	A more competitive and transparent business environment and more effective consumer protection mechanisms.

Programme performance in 2024

Oman operationalizes an integrated and evidence-based national development planning framework

22.85	As part of its effort to advance public policy across the Arab region, including by promoting effective governance and sustainable development, the subprogramme supported Oman in conducting a midterm assessment of its tenth five-year national development plan (2021–2025). The assessment evaluated economic, governance, social and environmental performance and tracked progress on 430 work programmes, 3,200 activities and 150 key performance indicators and their alignment with Oman Vision 2040 and the 2030 Agenda. Specifically, in order to foster transparency and stakeholder engagement, the subprogramme developed a dynamic platform that allowed Oman’s 55 implementing entities to update data by priority, strategic goal, activity and key performance indicator, enhancing accountability and proactive problem-solving. This was followed by a facilitated consultative process, during which the assessment results served as a basis for the identification of challenges and opportunities for accelerating the plan’s implementation. The support culminated in Oman identifying ways to enhance implementation and guide planning as it embarked on defining its next five-year development plan.

22.86	Progress towards the objective is presented in the performance measure below (see table 22.27).

Table 22.27

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) |
| --- | --- | --- |
| – | – | One member State (Oman) operationalized integrated and evidence-based national development planning |

Planned results for 2026

Result 1: improved consumer protection in the Arab region

Programme performance in 2024 and target for 2026

22.87	The subprogramme’s work contributed to member States exchanging knowledge and good practice on consumer protection and two member States (Egypt and United Arab Emirates) reforming their consumer protection laws, which met the planned target.

22.88	Progress towards the objective and the target for 2026 are presented in the performance measure below (see table 22.28).

Table 22.28

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| All 20 Arab member States participated in the third competition forum for the Arab region | Arab policymakers gained access to recommendations on how to improve national consumer protection frameworks | Member States exchanged knowledge and good practice on consumer protection | One additional member State establishes or reforms its consumer protection laws or enforcement procedures | Two additional member States establish new or reform existing consumer protection laws, to align them with international best practices |
| One member State (Lebanon) introduced competition legislation, and one additional member State (Kuwait) introduced further legislation on competition | Arab member States gained access to the Arab Legislation Portal, comprising information on existing consumer protection laws and regulations | Two member States (Egypt and United Arab Emirates) reformed their consumer protection laws |  |  |
| One member State (Oman) expanded its dedicated competition authority |  |  |  |  |

Result 2: modernization of public administration systems for effective and transparent public governance and socioeconomic development

Programme performance in 2024 and target for 2026

22.89	The subprogramme’s work contributed to three member States (Saudi Arabia, United Arab Emirates and Yemen) developing transparency measures to combat corruption in the public sector and member States reaching an agreement to convene on an annual basis on anti-corruption measures, which exceeded the planned target of one member State developing transparency measures to combat corruption in the public sector.

22.90	Progress towards the objective and the target for 2026 are presented in the performance measure below (see table 22.29).

Table 22.29

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| – | Member States receive advice on workable solutions to systemic challenges facing their public administration systems for more effective public service delivery | Three member States (Saudi Arabia, United Arab Emirates and Yemen) developed transparency measures to combat corruption in the public sector | One member State introduces reforms to modernize its public administration system | One additional member State introduces reforms to modernize its public administration system |
|  |  | Member States reached an agreement to convene on anti-corruption measures on an annual basis during the second regional dialogue on corruption (Arab Forum against Corruption) |  |  |

Result 3: member States develop and deploy development policies resilient to fragility and sudden shocks

Proposed programme plan for 2026

22.91	By 2023, some 76.8 million people across seven Arab countries in conflict or post-conflict settings (16.3 per cent of the region’s population) required humanitarian assistance. The subprogramme launched a regional initiative to foster transitions towards durable peace and development through a combined evidence-based and consensus-building approach that aligned national priorities in humanitarian, development and peacebuilding fields.

Lessons learned and planned change

22.92	The lesson for the subprogramme was that building resilience and enabling sustainable recovery required targeted capacity-building to enable the public sector to effectively deliver services and foster trust. In applying the lesson, the subprogramme will enhance its capacity-building support to public institutions and other relevant national stakeholders to enable the design of policies that are resilient and adaptable to crises. In parallel, the Commission will engage member States and United Nations resident coordinators to develop operational frameworks and national implementation strategies that more effectively integrate humanitarian, development and peace efforts, thereby facilitating smoother transitions toward recovery and achieving the Sustainable Development Goals.

22.93	Expected progress towards the objective is presented in the performance measure below (see table 22.30).

Table 22.30

Performance measure

| 2022 (actual) | 2023 (actual) | 2024 (actual) | 2025 (planned) | 2026 (planned) |
| --- | --- | --- | --- | --- |
| – | – | Nine member States (Iraq, Jordan, Lebanon, Libya, Somalia, the Sudan, the Syrian Arab Republic and Yemen, as well as the State of Palestine) adopted the regional standard operating procedure on operationalizing integrated humanitarian, development and peace approaches in fragile settings | Two member States have enhanced capacity to integrate recovery readiness and resilience into sustainable development initiatives | Two member States develop integrated national recovery, resilience and development strategies/plans |

Deliverables

22.94	Table 22.31 lists all deliverables of the subprogramme.

Table 22.31

Subprogramme 6: deliverables for 2024–2026, by category and subcategory

| Category and subcategory | 2024 planned | 2024 actual | 2025 planned | 2026 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Parliamentary documentation (number of documents) | 2 | 1 | 2 | 2 |
| 1. Note by the Secretary-General on the economic and social repercussions of the Israeli occupation on the living conditions of the Palestinian people in the Occupied Palestinian Territory, including East Jerusalem, and the Arab population in the occupied Syrian Golan to the General Assembly and the Economic and Social Council | 1 | 1 | 1 | 1 |
| 2. Reports to the ESCWA ministerial session on the social and economic impact of the Israeli occupation: thematic focus | 1 | – | 1 | 1 |
| Substantive services for meetings (number of three-hour meetings) | – | 8 | 4 | 8 |
| 3. High-level meeting of the League of Arab States/Arab Administrative Development Organization/ESCWA | – | 4 | 4 | 4 |
| 4. Arab Competition Forum | – | 4 | – | 4 |
| B. Generation and transfer of knowledge |  |  |  |  |
| Field and technical cooperation projects (number of projects) | 4 | 4 | 3 | 1 |
| 5. Country-specific and regional projects (implementation of the Doha Programme of Action in Arab least developed countries; development under occupation in the State of Palestine; integrating peace, recovery and development into conflict and post-conflict settings; and competition) | 4 | 4 | 3 | 1 |
| Seminars, workshops and training events (number of days) | 8 | 9 | 9 | 9 |
| 6. Competition and consumer protection | 1 | 1 | 1 | 1 |
| 7. Governance and major sub-indices (governance, human development index, conflict and the environment) | 1 | 2 | 1 | 2 |
| 8. Comprehensive risk assessment framework and conflict prevention, recovery and stabilization | 1 | 2 | 1 | 2 |
| 9. Strategic planning in fragile contexts; effectiveness of basic service delivery; and integrated approach for humanitarian development and peace in countries in conflict and post-conflict settings | 5 | 4 | 6 | 4 |
| Publications (number of publications) | 2 | 1 | 3 | 2 |
| 10. On governance and conflict prevention; and the strengthening of public institutions | 1 | 1 | 1 | 1 |
| 11. Palestine under Occupation | 1 | – | – | – |
| 12. The Arab Business Legislative Framework | – | – | 1 | 1 |
| 13. Arab Development Challenges Report | – | – | 1 | – |
| Technical materials (number of materials) | 8 | 10 | 8 | 9 |
| 14. On durable peace; vulnerability assessments and risk mitigation; conflict prevention, post-conflict recovery and stabilization; institution-building to strengthen resilience, performance and service provision; innovation in the public sector; economic governance; mitigating the impact of occupation; sustainable development in situations of conflict and post-conflict; and impact of competition reforms on trade policy; and human development and human securitya | 8 | 10 | 8 | 9 |
| C. Substantive deliverables |  |  |  |  |
| Consultation, advice and advocacy: consultative meetings on post-conflict and durable peace; vulnerability assessments and risk mitigation; conflict prevention, post-conflict recovery and stabilization; institution-building to strengthen resilience; innovation in the public sector; public service delivery; economic governance; mitigating the impact of occupation; and advocacy for policy dialogue. |  |  |  |  |
| Database and other substantive digital materials: portal on open government and open data; Arab legislation portal; ESCWA violence early warning system portal; and Arab national development planning portal. |  |  |  |  |
| D. Communications deliverables |  |  |  |  |
| Outreach programmes, special events and information materials: observance of the International Day of Solidarity with the Palestinian people; and materials on the impact of conflict and occupation on the socioeconomic development of the Palestinian people. |  |  |  |  |

a 	See General Assembly resolution 66/290.

B.	Proposed post and non-post resource requirements for 2026

Note: The following abbreviations are used in the tables and figures: FS, Field Service; LL, Local level; NPO, National Professional Officer; USG, Under-Secretary-General.

Overview

22.95	The proposed regular budget resources for 2026, including the breakdown of resource changes, as applicable, are reflected in tables 22.32 to 22.34.

Table 22.32

Overall: evolution of financial resources by object of expenditure

(Thousands of United States dollars)

| Object of expenditure |  |  | Changes |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2024 expenditurea | 2025 approved | Technical adjustments | New/expanded mandates | Other | Total | Percentage | 2026 estimate |
| Posts | 41 793.2 | 40 137.3 | – | – | 32.5 | 32.5 | 0.1 | 40 169.8 |
| Other staff costs | 2 369.0 | 1 733.6 | – | – | 172.0 | 172.0 | 9.9 | 1 905.6 |
| Hospitality | 1.4 | 10.5 | – | – | – | – | – | 10.5 |
| Consultants | 331.0 | 804.2 | – | – | (32.5) | (32.5) | (4.0) | 771.7 |
| Experts | 467.8 | 1 245.1 | – | – | – | – | – | 1 245.1 |
| Travel of staff | 443.5 | 446 | – | – | – | – | – | 446.0 |
| Contractual services | 1 876.6 | 1 878.6 | – | – | 265.7 | 265.7 | 14.1 | 2 144.3 |
| General operating expenses | 2 829.8 | 4 147.5 | – | – | (427.1) | (427.1) | (10.3) | 3 720.4 |
| Supplies and materials | 30.0 | 22.5 | – | – | – | – | – | 22.5 |
| Furniture and equipment | 613.0 | 726.9 | – | – | – | – | – | 726.9 |
| Grants and contributions | 1.1 | – | – | – | – | – | – | – |
| Total | 50 756.4 | 51 152.2 | – | – | 10.6 | 10.6 | 0.0 | 51 162.8 |

a	At the time of reporting, the expenditure presented in this table and in subsequent tables is not final and may be subject to adjustments that could result in minor differences between the information contained in the present report and the financial statements to be issued by 31 March 2025.

Table 22.33

Overall: proposed posts and post changes for 2026

(Number of posts)

|  | Number | Details |
| --- | --- | --- |
| Approved for 2025 | 257 | 1 USG, 2 D-2, 8 D-1, 25 P-5, 37 P-4, 30 P-3, 18 P-2/1, 1 FS, 4 NPO, 131 LL |
| Redeployment | – | 1 P-5, 6 P-4, 4 P-3, 1 NPO, 18 LL from programme support to executive direction and management 1 Programme Management Officer (NPO) from executive direction and management to programme support |
| Reclassification | – | 1 Medical Officer (P-4) to Senior Medical Officer (P-5) in programme support |
| Proposed for 2026 | 257 | 1 USG, 2 D-2, 8 D-1, 26 P-5, 36 P-4, 30 P-3, 18 P-2/1, 1 FS, 4 NPO, 131 LL |

Table 22.34

Overall: proposed posts by category and gradea

(Number of posts)

| Category and grade | 2025 approved | Changes |  |  |  | 2026 proposed |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Technical adjustments | New/expanded mandates | Other | Total |  |
| Professional and higher |  |  |  |  |  |  |
| USG | 1 | – | – | – | – | 1 |
| D-2 | 2 | – | – | – | – | 2 |
| D-1 | 8 | – | – | – | – | 8 |
| P-5 | 25 | – | – | 1 | 1 | 26 |
| P-4 | 37 | – | – | (1) | (1) | 36 |
| P-3 | 30 | – | – | – | – | 30 |
| P-2/1 | 18 | – | – | – | – | 18 |
| Subtotal | 121 | – | – | – | – | 121 |
| General Service and related |  |  |  |  |  |  |
| FS | 1 | – | – | – | – | 1 |
| NPO | 4 | – | – | – | – | 4 |
| LL | 131 | – | – | – | – | 131 |
| Subtotal | 136 | – | – | – | – | 136 |
| Total | 257 | – | – | – | – | 257 |

a	Includes four temporary posts (1 P-4, 2 P-3 and 1 Local level), which were approved pursuant to General Assembly resolution 71/272 A.

22.96	Additional details on the distribution of the proposed resources for 2026 are reflected in tables 22.35 to 22.37 and figure 22.I.

22.97	As shown in tables 22.35 (1) and 22.36 (1), the overall resources proposed for 2026 amount to $51,162,800, reflecting a net increase of $10,600 (0.0 per cent) compared with the approved budget for 2025. Resource changes result from other changes. The proposed level of resources provides for the full, efficient and effective implementation of mandates.

Table 22.35

Overall: evolution of financial resources by source of funding, component and subprogramme

(Thousands of United States dollars)

(1)	Regular budget

| Component/subprogramme | 2024 expenditure | 2025 approved | Changes |  |  |  |  | 2026 estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Technical adjustments | New/expanded mandates | Other | Total | Percentage |  |
| A. Policymaking organs | 117.4 | 146.0 | – | – | – | – | – | 146.0 |
| B. Executive direction and management | 6 131.1 | 8 511.5 | – | – | 4 794.9 | 4 794.9 | 56.3 | 13 306.4 |
| C. Programme of work |  |  |  |  |  |  |  |  |
| 1. Climate change and natural resource sustainability | 4 402.6 | 4 253.3 | – | – | (50.0) | (50.0) | (1.2) | 4 203.3 |
| 2. Gender justice, population and inclusive development | 5 951.5 | 5 794.1 | – | – | (48.8) | (48.8) | (0.8) | 5 745.3 |
| 3. Shared economic prosperity | 4 689.1 | 4 886.5 | – | – | – | – | – | 4 886.5 |
| 4. Statistics, the information society and technology | 5 452.1 | 4 824.3 | – | – | 23.1 | 23.1 | 0.5 | 4 847.4 |
| 5. 2030 Agenda and SDG coordination | 2 358.4 | 2 473.1 | – | – | – | – | – | 2 473.1 |
| 6. Governance and conflict prevention | 3 257.6 | 3 518.9 | – | – | (25.6) | (25.6) | (0.7) | 3 493.3 |
| Subtotal, C | 26 111.2 | 25 750.2 | – | – | (101.3) | (101.3) | (0.4) | 25 648.9 |
| D. Programme support | 18 396.7 | 16 744.5 | – | – | (4 683.0) | (4 683.0) | (28.0) | 12 061.5 |
| Subtotal, 1 | 50 756.4 | 51 152.2 | – | – | 10.6 | 10.6 | 0.0 | 51 162.8 |

(2) 	Extrabudgetary

| Component/subprogramme | 2024 expenditure | 2025 estimate |  | Change | Percentage | 2026 estimate |
| --- | --- | --- | --- | --- | --- | --- |
| A. Policymaking organs | – | – |  | – | – | – |
| B. Executive direction and management | 700.6 | 1 931.4 |  | (769.4) | (39.8) | 1 162.0 |
| C. Programme of work |  |  |  |  |  |  |
| 1. Climate change and natural resource sustainability | 2 172.8 | 2 044.4 |  | 2 750.3 | 134.5 | 4 794.7 |
| 2. Gender justice, population and inclusive development | 1 404.9 | 1 285.6 |  | (689.1) | (53.6) | 596.5 |
| 3. Shared economic prosperity | 1 130.4 | 1 795.4 |  | (556.5) | (31.0) | 1 238.9 |
| 4. Statistics, the information society and technology | 230.9 | 198.2 |  | (198.2) | (100.0) | – |
| 5. 2030 Agenda and SDG coordination | – | – |  | – | – | – |
| 6. Governance and conflict prevention | 359.7 | 616.8 |  | (616.8) | (100.0) | – |
| Subtotal, C | 5 298.7 | 5 940.4 |  | 689.7 | 11.6 | 6 630.1 |
| D. Programme support | 4 253.5 | 4 253.5 |  | 397.2 | 9.3 | 4 650.7 |
| Subtotal, 2 | 10 252.8 | 12 125.3 |  | 317.5 | 2.6 | 12 442.8 |
| Total (1+2) | 61 009.2 | 63 277.5 |  | 328.1 | 0.5 | 63 605.6 |

Table 22.36

Overall: proposed posts for 2026 by source of funding, component and subprogramme

(Number of posts)

(1)	Regular budget

|  |  | Changes |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Component/subprogramme | 2025 approved | Technical adjustments | New/expanded mandates | Other | Total | 2026 proposed |
| A. Policymaking organs | – | – | – | – | – | – |
| B. Executive direction and management | 44 | – | – | 29 | 29 | 73 |
| C. Programme of work |  |  |  |  |  |  |
| 1. Climate change and natural resource sustainability | 22 | – | – | – | – | 22 |
| 2. Gender justice, population and inclusive development | 29 | – | – | – | – | 29 |
| 3. Shared economic prosperity | 27 | – | – | – | – | 27 |
| 4. Statistics, the information society and technology | 27 | – | – | – | – | 27 |
| 5. 2030 Agenda and SDG coordination | 10 | – | – | – | – | 10 |
| 6. Governance and conflict prevention | 17 | – | – | – | – | 17 |
| Subtotal, C | 132 | – | – | – | – | 132 |
| D. Programme support | 81 | – | – | (29) | (29) | 52 |
| Subtotal, 1 | 257 | – | – | – | – | 257 |

(2)	Extrabudgetary

| Component/subprogramme | 2025 estimate | Change | 2026 estimate |
| --- | --- | --- | --- |
| A. Policymaking organs | – | – | – |
| B. Executive direction and management | 8 | (1) | 7 |
| C. Programme of work |  |  |  |
| 1. Climate change and natural resource sustainability | 8 | 7 | 15 |
| 2. Gender justice, population and inclusive development | 3 | (1) | 2 |
| 3. Shared economic prosperity | 5 | (2) | 3 |
| 4. Statistics, the information society and technology | 1 | (1) | – |
| 5. 2030 Agenda and SDG coordination | – | – | – |
| 6. Governance and conflict prevention | 2 | (2) | – |
| Subtotal, C | 19 | 1 | 20 |
| D. Programme support | 16 | 2 | 18 |
| Subtotal, 2 | 43 | 2 | 45 |
| Total (1+2) | 300 | 2 | 302 |

Table 22.37

Overall: evolution of financial and post resources

(Thousands of United States dollars/number of posts)

|  | 2024 expenditure | 2025 approved | Changes |  |  |  |  | 2026 estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Technical adjustments | New/expanded mandates | Other | Total | Percentage |  |
| Financial resources by main category of expenditure |  |  |  |  |  |  |  |  |
| Posts | 41 793.2 | 40 137.3 | – | – | 32.5 | 32.5 | 0.1 | 40 169.8 |
| Non-post | 8 963.2 | 11 014.9 | – | – | (21.9) | (21.9) | (0.2) | 10 993.0 |
| Total | 50 756.4 | 51 152.2 | – | – | 10.6 | 10.6 | 0.0 | 51 162.8 |
| Post resources by category |  |  |  |  |  |  |  |  |
| Professional and higher |  | 121 | – | – | – | – | – | 121 |
| General Service and related |  | 136 | – | – | – | – | – | 136 |
| Total |  | 257 | – | – | – | – | – | 257 |

Figure 22.I

Distribution of proposed resources for 2026

(Number of posts/thousands of United States dollars)

Explanation of variances by factor, component and subprogramme

Overall resource changes

Other changes

22.98	As shown in table 22.35 (1), resource changes reflect a net increase of $10,600, representing an increase under contractual services reflecting a higher standard price of the core software package for non-field personnel outside of United Nations Headquarters; the other changes, which include the upgrade of a P-4 post to a P-5 post and the redeployment of post and non-post resources between executive direction and management and programme support, are overall cost-neutral. The details of other changes are as follows:

(a)	Executive direction and management. The net increase of $4,794,900 relates mainly to the proposed redeployment of the Conference Management Section as the Knowledge Management Service under executive direction and management, entailing the following:

(i)	The inward redeployment of 30 posts (1 P-5, 6 P-4, 4 P-3, 1 National Professional Officer and 18 Local level) from programme support, as reflected in annex II to the present report ($4,232,400);

(ii)	The inward redeployment of requirements under travel ($8,500), contractual services ($207,900), general operating expenses ($25,800) and furniture and equipment ($17,200) to consolidate and streamline the content delivery and knowledge management capacity of the Commission, including intellectual support and language, documentation and conference services under the component. Justification for the proposed redeployment is provided in annex I to the present report;

(iii)	Increased requirements under other staff costs ($127,000), consultants ($33,800) and contractual services ($190,100) reflect mainly the need to strengthen the capacity to design, develop and maintain specialized data solutions for member States;

(iv)	The increased requirements under experts ($100,000) to provide for high-level expert group meetings in support of the decision support system and data science and of the small and medium-sized enterprise forum;

(v)	The aforementioned increases are offset in part by the outward redeployment of one post of Programme Management Officer (National Professional Officer) to programme support, as reflected in annex II ($147,800);

(b)	Subprogramme 1, Climate change and natural resources. The decrease of $50,000 under experts relates to the anticipated streamlining of activities into interrelated events and back-to-back meetings;

(c)	Subprogramme 2, Gender justice, population, and inclusive development. The net decrease of $48,800 relates to reduced requirements under experts ($50,000) and travel of staff ($14,900), reflecting the anticipated streamlining of activities into interrelated events and back-to-back meetings, offset in part by the increased requirements under contractual services ($16,100), reflecting higher anticipated requirements for the development of enhanced and customized technical tools on gender justice, poverty reduction and social protection;

(d)	Subprogramme 4, Statistics, the information society and technology. The increase ($23,100) under contractual services reflects the anticipated increase in the requirements for individual contractors to strengthen capacity in price statistics, digital development and statistical support to ensure the delivery of high-quality data and technical expertise for key initiatives;

(e)	Subprogramme 6, Governance and conflict prevention. The net decrease ($25,600) relates to reduced requirements under consultants ($43,100), reflecting the leveraging of technology solutions, such as data analytics, artificial intelligence and collaborative platforms, to streamline processes and analysis required for decision-making, offset in part by the increased requirements under contractual services ($17,500), reflecting higher anticipated requirements for enhanced and customized technical and policy tools that will provide specialized expertise in conflict prevention and recovery, institution-building, sustainable development in post-conflict settings, competition reforms in trade policy and human development, ensuring the effective delivery of the ESCWA mandate;

(f)	Programme support. The net decrease of $4,683,000 relates to:

(i)	The outward redeployment of 30 posts (1 P-5, 6 P-4, 4 P-3, 1 National Professional Officer and 18 Local level) to the Knowledge Management Service under executive direction and management ($4,232,400), as reflected in annex II;

(ii)	The outward redeployment of the requirements under travel of staff ($8,500), contractual services ($207,900), general operating expenses ($25,800) and furniture and equipment ($17,200) to consolidate and streamline the content delivery and knowledge management capacity, including intellectual support and language, documentation and conference services under executive direction and management;

(iii)	Reduced requirements under general operating expenses ($427,100), reflecting mainly the anticipated decrease in energy use in the ESCWA building, including through the optimization of the heating, ventilation and air-conditioning systems and the adoption of energy-efficient lighting and other smart building management systems;

(iv)	Offset in part by the following:

a.	The upward reclassification of one post of Medical Officer (P-4) to Senior Medical Officer (P-5) ($32,500), as reflected in annex II;

b.	The inward redeployment of one post of Programme Management Officer (National Professional Officer) from executive direction and management ($147,800), as reflected in annex II;

c.	Increased requirements under other staff costs ($45,000), reflecting the need to strengthen the capacity to design, develop and maintain specialized data solutions for member States;

d.	Increased requirements under contractual services ($10,600) relating to a higher standard price of the core software package for non-field personnel outside of Headquarters.

Extrabudgetary resources

22.99	As reflected in tables 22.33 (2) and 22.34 (2), extrabudgetary resources amount to $12,442,800. The resources would complement regular budget resources and would be used mainly to provide for 45 posts (1 D-1, 1 P-5, 3 P-4, 3 P-3, 1 P-2, 4 National Professional Officer and 32 Local level) to perform various functions, including in the areas of economic development, sustainable development, administration and coordination. In addition, non-post resources would be used for strengthening data and information capabilities, promoting coordinated multisectoral interventions in such areas as energy, agriculture and food systems, water, gender equality, job creation and youth empowerment, decision support and data science, establishing portals and platforms for the Sustainable Development Goals to support the Arab region’s digital revolution, enhancing initiatives in sustainable energy transitions, social protection, economic empowerment of persons with disabilities, and training programmes for artificial intelligence technologies and business models. In essence, the funds are intended to boost the region’s capacity for sustainable development through improved data, coordination and targeted initiatives across various sectors, with a strong focus on digital transformation and modern technologies such as artificial intelligence.

22.100	The extrabudgetary resources under the present section are subject to the oversight of the secretariat of ESCWA, which has delegated authority from the Secretary-General.

Policymaking organs

22.101	The resources proposed under this component would provide for the policymaking organs as shown in table 22.38.

Table 22.38

Policymaking organs

(Thousands of United States dollars)

| Policymaking organ | Additional information | 2025 approved | 2026 estimate |
| --- | --- | --- | --- |
| Executive Committee | Mandate: ESCWA resolution 320 (XXVIII) | 15 | 15 |
|  | Membership: 21 government officials |  |  |
|  | Number of sessions in 2026: 1 |  |  |
| Statistical Committee | Mandate: ESCWA resolution 179 (XVI), as endorsed by the Economic and Social Council in its resolution 1993/2 | – | – |
|  | Membership: 21 government officials |  |  |
|  | Number of sessions in 2026: – |  |  |
| Committee on Transport and Logistics | Mandate: ESCWA resolution 213 (XIX), as endorsed by the Economic and Social Council in its resolution 1997/11, and ESCWA resolution 229 (XXI) | 20 | 20 |
|  | Membership: 21 government officials |  |  |
|  | Number of sessions in 2026: 1 |  |  |
| Committee on Technology for Development | Mandate: ESCWA resolution 315 (XXVIII), as endorsed by the Economic and Social Council in its resolution 2014/35 | – | – |
|  | Membership: 21 government officials |  |  |
|  | Number of sessions in 2026: – |  |  |
| Committee on Trade Policies in the States members of the Economic and Social Commission for Western Asia | Mandate: ESCWA resolution 332 (XXX), as endorsed by the Economic and Social Council in its resolution 2019/30 | – | – |
|  | Membership: 21 government officials |  |  |
|  | Number of sessions in 2026: – |  |  |
| Committee on Energy | Mandate: ESCWA resolution 204 (XVIII), as endorsed by the Economic and Social Council in its resolution 1995/25 | 20 | 20 |
|  | Membership: 21 government officials |  |  |
|  | Number of sessions in 2026: 1 |  |  |
| Committee on Water Resources | Mandate: ESCWA resolution 205 (XVIII), as endorsed by the Economic and Social Council in its resolution 1995/26 | 20 | 18 |
|  | Membership: 21 government officials |  |  |
|  | Number of sessions in 2026: 1 |  |  |
| Committee on Social Development | Mandate: ESCWA resolution 198 (XVII), as endorsed by the Economic and Social Council in its resolution 1994/27, and ESCWA resolution 344 (XXXI) on the frequency of sessions of the Committee (annual sessions starting in 2026) | 20 | 20 |
|  | Membership: 21 government officials |  |  |
|  | Number of sessions in 2026: 1 |  |  |
| Committee on Financing for Development in the States members of the Economic and Social Commission for Western Asia | Mandate: ESCWA resolution 332 (XXX), as endorsed by the Economic and Social Council in its resolution 2019/30 | 18 | 20 |
|  | Membership: 21 government officials |  |  |
|  | Number of sessions in 2026: 1 |  |  |
| Committee on Women | Mandate: ESCWA resolution 240 (XXII), as endorsed by the Economic and Social Council in its resolution 2003/9 | 18 | 18 |
|  | Membership: 21 government officials |  |  |
|  | Number of sessions in 2026: 1 |  |  |
| ESCWA session | Mandate: Economic and Social Council resolution 1818 (LV) | 15 | 15 |
|  | Membership: 21 government officials |  |  |
|  | Number of sessions in 2026: 1 |  |  |
| Total |  | 146.0 | 146.0 |

22.102	The proposed regular budget resources for 2026 amount to $146,000 and reflect no change compared with the approved budget for 2025.

Table 22.39

Policymaking organs: evolution of financial resources

(Thousands of United States dollars)

|  | 2024 expenditure | 2025 approved | Changes |  |  |  |  | 2026 estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Technical adjustments | New/expanded mandates | Other | Total | Percentage |  |
| Financial resources by main category of expenditure |  |  |  |  |  |  |  |  |
| Non-post | 117.4 | 146.0 | – | – | – | – | – | 146.0 |
| Total | 117.4 | 146.0 | – | – | – | – | – | 146.0 |

Figure 22.II

Policymaking organs: distribution of proposed resources for 2026

(Thousands of United States dollars)

Executive direction and management

22.103	The Office of the Executive Secretary is responsible for coordinating and providing overall leadership, policy direction and management of the ESCWA secretariat to support member States, in collaboration with other entities of the United Nations system, with strategic analysis, policy guidelines and capacity-building activities to address key development challenges and issues and to implement innovative solutions for region-wide equitable and inclusive economic prosperity, social progress and environmental sustainability. The Office provides leadership and policy orientation and establishes criteria to coordinate follow-up in the region on implementing the 2030 Agenda and the Addis Ababa Action Agenda of the Third International Conference on Financing for Development, and the mainstreaming of cross-cutting issues, such as gender equality and the empowerment of women, and sustainability perspectives, throughout ESCWA substantive programmes. The Knowledge Management Service will provide alignment with the Commission’s strategic planning and project cycles, improving agility and responsiveness to programmatic needs. In addition, the Service will provide expertise in communication, content quality and multilingual support, reinforcing role of ESCWA as a knowledge-driven organization, while enhancing its visibility and coherence.

22.104	The role of ESCWA in supporting evidence-based policymaking and innovation, together with its commitment to the Secretary-General’s strategies on data and new technologies, will ensure that the Arab region is not only a beneficiary of the digital revolution, but also an active contributor to the global dialogue on sustainable development through technology. The Decision Support and Data Science Division will provide foresight and analysis of regional and global trends, as well as evidence pertaining to sustainable development, necessary for informed policymaking, and will bolster innovation and the roll-out of information and communications technology solutions in support of member States and the Commission’s programme delivery, including through coordination across its six subprogrammes.

22.105	The Office reinforces policy consistency and coherence and promotes effective collaboration and coordination, both within the ESCWA secretariat and among United Nations entities and development partners involved in addressing regional development issues, including through the Regional Coordination Mechanism for Arab States. It also strengthens cooperation and coordination with international and regional intergovernmental and non-governmental organizations, especially the League of Arab States and its subsidiary bodies.

22.106	The Strategy, Planning, Accountability, Results and Knowledge Section will continue to promote dynamism and innovation in the ESCWA business model and medium-term strategy and to act as a focal point for the annual results framework and related applications in Umoja. The Section will continue to be the basis for organizational learning processes, focusing on accountability and on the attainment of results, and ensuring the operational excellence of ESCWA through risk reduction and change management processes. The Section will continue to manage the broader knowledge and dissemination processes of the Commission.

22.107	The Resource Mobilization and Partnerships Section will continue to strengthen relationships with funding agencies and donors; maintain up-to-date regional and global donor mapping; coordinate and support project development, budgeting and fundraising; support and track the implementation of extrabudgetary projects; assist ESCWA cluster leaders in building and enhancing institutional partnerships (regional and global); support cluster leaders’ relationships with civil society and non-State actors and partners; and develop and negotiate legally binding partnerships and donor agreements.

22.108	In accordance with the 2030 Agenda, in particular target 12.6 of the Sustainable Development Goals, in which organizations are encouraged to integrate sustainability information into their reporting cycles, and in compliance with the cross-cutting mandate set out in paragraph 19 of General Assembly resolution 72/219, the Commission integrates environmental management practices into its operations. In 2026, the Commission will: (a) facilitate dialogue and collaboration among stakeholders to foster policy coherence, knowledge-sharing and capacity-building initiatives that support the implementation of the 2030 Agenda; (b) provide technical assistance and advisory services to member States, helping to strengthen institutional frameworks, enhance data-driven decision-making and integrate sustainable development goals into national policies and strategies; and (c) promote innovative financing mechanisms and resource mobilization efforts to bridge funding gaps and support sustainable, inclusive economic growth across the region.

22.109	Information on the timely submission of documentation and advance booking for air travel is reflected in table 22.40. ESCWA has made efforts to raise awareness among staff of the requirement to comply with the advance purchase guidance and, in this context, has put in place a procedure whereby travel requests not compliant with the advance booking policy have to be cleared by the Office of the Executive Secretary to hold project managers accountable for the late travel-related submissions. As a result of these measures, there has been a continuous improvement in the compliance rate. The Commission will continue its efforts to achieve its targets in 2026. It will enhance compliance with advance travel booking through regular monitoring, strengthened accountability and performance benchmarking. These measures are intended to sustain improvements, promote cost-effective travel planning and ensure operational efficiency.

Table 22.40

Compliance rate

(Percentage)

|  | 2022 actual | 2023 actual | 2024 actual | 2025 planned | 2026 planned |
| --- | --- | --- | --- | --- | --- |
| Timely submission of documentation | 70 | 88 | 92 | 100 | 100 |
| Air tickets purchased at least two weeks before the commencement of travel | 57 | 60 | 80 | 100 | 100 |

22.110	The proposed regular budget resources for 2026 amount to $13,306,400 and reflect a net increase of $4,794,900 compared with the approved budget for 2025. The proposed change is explained in paragraph 22.98 (a) above. Additional details on the distribution of the proposed resources for 2026 are reflected in table 22.41 and figure 22.III.

Table 22.41

Executive direction and management: evolution of financial and post resources

(Thousands of United States dollars/number of posts)

|  | 2024 expenditure | 2025 approved | Changes |  |  |  |  | 2026 estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Technical adjustments | New/expanded mandates | Other | Total | Percentage |  |
| Financial resources by main category of expenditure |  |  |  |  |  |  |  |  |
| Posts | 5 122.4 | 7 017.8 | – | – | 4 084.6 | 4 084.6 | 58.2 | 11 102.4 |
| Non-post | 1 008.7 | 1 493.7 | – | – | 710.3 | 710.3 | 47.6 | 2 204.0 |
| Total | 6 131.1 | 8 511.5 | – | – | 4 794.9 | 4 794.9 | 56.3 | 13 306.4 |
| Post resources by category |  |  |  |  |  |  |  |  |
| Professional and higher |  | 20 | – | – | 11 | 11 | 55.0 | 31 |
| General Service and related |  | 24 | – | – | 18 | 18 | 75.0 | 42 |
| Total |  | 44 | – | – | 29 | 29 | 65.9 | 73 |

Figure 22.III

Executive direction and management: distribution of proposed resources for 2026

(Number of posts/thousands of United States dollars)

Programme of work

Subprogramme 1

Climate change and natural resource sustainability

22.111	The proposed regular budget resources for 2026 amount to $4,203,300 and reflect a net decrease of $50,000 compared with the approved budget for 2025. The proposed change is explained in paragraph 22.98 (b) above. Additional details on the distribution of the proposed resources for 2026 are reflected in table 22.42 and figure 22.IV.

Table 22.42

Subprogramme 1: evolution of financial and post resources

(Thousands of United States dollars/number of posts)

|  | 2024 expenditure | 2025 approved | Changes |  |  |  |  | 2026 estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Technical adjustments | New/expanded mandates | Other | Total | Percentage |  |
| Financial resources by main category of expenditure |  |  |  |  |  |  |  |  |
| Posts | 4 312.5 | 3 824.6 | – | – | – | – | – | 3 824.6 |
| Non-post | 90.1 | 428.7 | – | – | (50.0) | (50.0) | (11.7) | 378.7 |
| Total | 4 402.6 | 4 253.3 | – | – | (50.0) | (50.0) | (1.2) | 4 203.3 |
| Post resources by category |  |  |  |  |  |  |  |  |
| Professional and higher |  | 13 | – | – | – | – | – | 13 |
| General Service and related |  | 9 | – | – | – | – | – | 9 |
| Total |  | 22 | – | – | – | – | – | 22 |

Figure 22.IV

Subprogramme 1: distribution of proposed resources for 2026

(Number of posts/thousands of United States dollars)

Subprogramme 2

Gender justice, population and inclusive development

22.112	The proposed regular budget resources for 2026 amount to $5,745,300 and reflect a net decrease of $48,800 compared with the approved budget for 2025. The proposed change is explained in paragraph 22.98 (c) above. Additional details on the distribution of the proposed resources for 2026 are reflected in table 22.43 and figure 22.V.

Table 22.43

Subprogramme 2: evolution of financial and post resources

(Thousands of United States dollars/number of posts)

|  | 2024 expenditure | 2025 approved | Changes |  |  |  |  | 2026 estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Technical adjustments | New/expanded mandates | Other | Total | Percentage |  |
| Financial resources by main category of expenditure |  |  |  |  |  |  |  |  |
| Posts | 5 349.5 | 5 172.4 | – | – | – | – | – | 5 172.4 |
| Non-post | 602.0 | 621.7 | – | – | (48.8) | (48.8) | (7.8) | 572.9 |
| Total | 5 951.5 | 5 794.1 | – | – | (48.8) | (48.8) | (0.8) | 5 745.3 |
| Post resources by category |  |  |  |  |  |  |  |  |
| Professional and higher |  | 19 | – | – | – | – | – | 19 |
| General Service and related |  | 10 | – | – | – | – | – | 10 |
| Total |  | 29 | – | – | – | – | – | 29 |

Figure 22.V

Subprogramme 2: distribution of proposed resources for 2026

(Number of posts/thousands of United States dollars)

Subprogramme 3

Shared economic prosperity

22.113	The proposed regular budget resources for 2026 amount to $4,886,500 and reflect no change compared with the approved budget for 2025. Additional details on the distribution of the proposed resources for 2026 are reflected in table 22.44 and figure 22.VI.

Table 22.44

Subprogramme 3: evolution of financial and post resources

(Thousands of United States dollars/number of posts)

|  | 2024 expenditure | 2025 approved | Changes |  |  |  |  | 2026 estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Technical adjustments | New/expanded mandates | Other | Total | Percentage |  |
| Financial resources by main category of expenditure |  |  |  |  |  |  |  |  |
| Posts | 4 513.0 | 4 414.1 | – | – | – | – | – | 4 414.1 |
| Non-post | 176.1 | 472.4 | – | – | – | – | – | 472.4 |
| Total | 4 689.1 | 4 886.5 | – | – | – | – | – | 4 886.5 |
| Post resources by category |  |  |  |  |  |  |  |  |
| Professional and higher |  | 15 | – | – | – | – | – | 15 |
| General Service and related |  | 12 | – | – | – | – | – | 12 |
| Total |  | 27 | – | – | – | – | – | 27 |

Figure 22.VI

Subprogramme 3: distribution of proposed resources for 2026

(Number of posts/thousands of United States dollars)

Subprogramme 4

Statistics, the information society and technology

22.114	The proposed regular budget resources for 2026 amount to $4,847,400 and reflect a net increase of $23,100 compared with the approved budget for 2025. The proposed change is explained in paragraph 22.98 (d) above. Additional details on the distribution of the proposed resources for 2026 are reflected in table 22.45 and figure 22.VII.

Table 22.45

Subprogramme 4: evolution of financial and post resources

(Thousands of United States dollars/number of posts)

|  | 2024 expenditure | 2025 approved | Changes |  |  |  |  | 2026 estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Technical adjustments | New/expanded mandates | Other | Total | Percentage |  |
| Financial resources by main category of expenditure |  |  |  |  |  |  |  |  |
| Posts | 4 699.2 | 4 354.2 | – | – | – | – | – | 4 354.2 |
| Non-post | 752.9 | 470.1 | – | – | 23.1 | 23.1 | 4.9 | 493.2 |
| Total | 5 452.1 | 4 824.3 | – | – | 23.1 | 23.1 | 0.5 | 4 847.4 |
| Post resources by category |  |  |  |  |  |  |  |  |
| Professional and higher |  | 14 | – | – | – | – | – | 14 |
| General Service and related |  | 13 | – | – | – | – | – | 13 |
| Total |  | 27 | – | – | – | – | – | 27 |

Figure 22.VII

Subprogramme 4: distribution of proposed resources for 2026

(Number of posts/thousands of United States dollars)

Subprogramme 5

2030 Agenda and SDG coordination

22.115	The proposed regular budget resources for 2026 amount to $2,473,100 and reflect no change compared with the approved budget for 2025. Additional details on the distribution of the proposed resources for 2026 are reflected in table 22.46 and figure 22.VIII.

Table 22.46

Subprogramme 5: evolution of financial and post resources

(Thousands of United States dollars/number of posts)

|  | 2024 expenditure | 2025 approved | Changes |  |  |  |  | 2026 estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Technical adjustments | New/expanded mandates | Other | Total | Percentage |  |
| Financial resources by main category of expenditure |  |  |  |  |  |  |  |  |
| Posts | 1 829.6 | 1 868.2 | – | – | – | – | – | 1 868.2 |
| Non-post | 528.8 | 604.9 | – | – | – | – | – | 604.9 |
| Total | 2 358.4 | 2 473.1 | – | – | – | – | – | 2 473.1 |
| Post resources by category |  |  |  |  |  |  |  |  |
| Professional and higher |  | 7 | – | – | – | – | – | 7 |
| General Service and related |  | 3 | – | – | – | – | – | 3 |
| Total |  | 10 | – | – | – | – | – | 10 |

Figure 22.VIII

Subprogramme 5: distribution of proposed resources for 2026

(Number of posts/thousands of United States dollars)

Subprogramme 6

Governance and conflict prevention

22.116	The proposed regular budget resources for 2026 amount to $3,493,300 and reflect a net decrease of $25,600 compared with the approved budget for 2025. The proposed change is explained in paragraph 22.98 (e) above. Additional details on the distribution of the proposed resources for 2026 are reflected in table 22.47 and figure 22.IX.

Table 22.47

Subprogramme 6: evolution of financial and post resources

(Thousands of United States dollars/number of posts)

|  | 2024 expenditure | 2025 approved | Changes |  |  |  |  | 2026 estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Technical adjustments | New/expanded mandates | Other | Total | Percentage |  |
| Financial resources by main category of expenditure |  |  |  |  |  |  |  |  |
| Posts | 3 104.0 | 3 138.1 | – | – | – | – | – | 3 138.1 |
| Non-post | 153.6 | 380.8 | – | – | (25.6) | (25.6) | (6.7) | 355.2 |
| Total | 3 257.6 | 3 518.9 | – | – | (25.6) | (25.6) | (0.7) | 3 493.3 |
| Post resources by category |  |  |  |  |  |  |  |  |
| Professional and higher |  | 11 | – | – | – | – | – | 11 |
| General Service and related |  | 6 | – | – | – | – | – | 6 |
| Total |  | 17 | – | – | – | – | – | 17 |

Figure 22.IX

Subprogramme 6: distribution of proposed resources for 2026

(Number of posts/thousands of United States dollars)

Programme support

22.117	Programme support comprises the Resource Management and Service Development Division. The component will continue to provide timely, effective and efficient administrative and logistical support to implement the Commission’s programme of work.

22.118	The proposed regular budget resources for 2026 amount to $12,061,500 and reflect a net decrease of $4,683,000 compared with the approved budget for 2025. The proposed change is explained in paragraph 22.98 (f) above. Additional details on the distribution of the proposed resources for 2026 are reflected in table 22.48 and figure 22.X.

Table 22.48

Programme support: evolution of financial and post resources

(Thousands of United States dollars/number of posts)

|  | 2024 expenditure | 2025 approved | Changes |  |  |  |  | 2026 estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Technical adjustments | New/expanded mandates | Other | Total | Percentage |  |
| Financial resources by main category of expenditure |  |  |  |  |  |  |  |  |
| Posts | 12 863.2 | 10 347.9 | – | – | (4 052.1) | (4 052.1) | (39.2) | 6 295.8 |
| Non-post | 5 533.5 | 6 396.6 | – | – | (630.9) | (630.9) | (9.9) | 5 765.7 |
| Total | 18 396.7 | 16 744.5 | – | – | (4 683.0) | (4 683.0) | (28.0) | 12 061.5 |
| Post resources by category |  |  |  |  |  |  |  |  |
| Professional and higher |  | 22 | – | – | (11) | (11) | (50.0) | 11 |
| General Service and related |  | 59 | – | – | (18) | (18) | (30.5) | 41 |
| Total |  | 81 | – | – | (29) | (29) | (35.8) | 52 |

Figure 22.X

Programme support: distribution of proposed resources for 2026

(Number of posts/thousands of United States dollars)

Annex I

Organizational structure and post distribution for 2026

Two charts showing the organizational structure of ESCWA are presented below. Chart A reproduces the approved organizational structure for 2025 as contained in A/79/6 (Sect. 22). Chart B presents the proposed organizational structure for 2026.

Justification for the proposed changes

The structural redeployment of the Conference Services Section from programme support as the Knowledge Management Service under executive direction and management reflects the Commission’s commitment to emphasizing efficiency, innovation and institutional learning. The Section operates at the intersection of content delivery and knowledge management, providing intellectual support through language, documentation and conference services integral to the work of ESCWA. The proposed redeployment of the Service would reinforce its ability to fulfil its role in enhancing ESCWA convening power, resonating with audiences and contributing substantively to the work programme. The proposed redeployment would facilitate closer integration with the ESCWA strategic planning and project cycles, fostering agility and responsiveness to the Commission’s programmatic needs. Such structural realignment would ensure that expertise in communication, content quality and multilingual support is more directly applied to enhance the mission of ESCWA and uphold its visibility and cohesion as a knowledge-driven organization. Moreover, positioning knowledge management services under executive direction and management aligns with United Nations-wide practices, by which conference and language services typically report directly to senior leadership. The proposed Service will report to the Executive Secretary through the Deputy Executive Secretary, Programme Support.

A.	Approved organizational structure and post distribution for 2025

Cluster 5: 2030 Agenda and SDG coordination

(subprogramme 5)

RB:

1 D-1

1 P-5

2 P-4

2 P-3

1 P-2

3 LL

Total: 10

Cluster 6: Governance and conflict prevention

(subprogramme 6)

| RB: | XB: |
| --- | --- |
| 1 D-1 | 1 P-4 |
| 3 P-5 | 1 P-3 |
| 4 P-4 |  |
| 2 P-3 |  |
| 1 P-2 |  |
| 6 LL |  |

17	2

Total: 19

Cluster 2: Gender justice, population and inclusive development (subprogramme 2)

| RB: | XB: |
| --- | --- |
| 1 D-1 | 2 LL |
| 5 P-5 |  |
| 5 P-4 |  |
| 4 P-3 |  |
| 4 P-2 |  |
| 10 LL |  |
| 29 | 2 |

Total: 31

Cluster 3: Shared economic prosperity

(subprogramme 3)

| RB: | XB: |
| --- | --- |
| 1 D-1 | 2 LL |
| 2 P-5 |  |
| 5 P-4 |  |
| 5 P-3 |  |
| 2 P-2 |  |
| 12 LL |  |
| 27 | 2 |

Total: 29

Cluster 4: Statistics, the information society and technology

(subprogramme 4)

| RB: | XB: |
| --- | --- |
| 1 D-1 | 1 P-5 |
| 3 P-5 | 1 LL |
| 4 P-4 |  |
| 4 P-3 |  |
| 2 P-2 |  |
| 1 NPO |  |
| 12 LL |  |
| 27 | 2 |

Total: 29

Resource Management and Service Development Division

(programme support)

| RB: | XB: |
| --- | --- |
| 1 D-1 | 3 P-4 |
| 3 P-5 | 2 P-3 |
| 8 P-4 | 1 NPO |
| 7 P-3 | 20 LL |
| 3 P-2 |  |
| 1 FS |  |
| 2 NPO |  |
| 56 LL |  |
| 81 | 26 |

Total: 107

Strategy, Planning, Accountability, Results and Knowledge Section

(executive direction and management)

RB:

1 P-5

1 P-4

1 P-3

1 P-2

6 LL

Total: 10

Resource Mobilization and Partnerships Section

(executive direction and management)

RB:

1 P-4

1 P-2

1 LL

Total: 3

Office of the Executive Secretary

(executive direction and management)

RB:

1 USG

2 D-2

1 D-1

2 P-5

2 P-4

1 P-3

1 P-2

1 NPO

8 LL

Total: 19

Decision Support and Data Science Division

(executive direction and management)

RB:

1 P-5

1 P-4

1 P-3

1 P-2

8 LL

Total: 12

Cluster 1: Climate change and natural resource sustainability

(subprogramme 1)

| RB: | XB: |
| --- | --- |
| 1 D-1 | 1 D-1 |
| 4 P-5 | 1 P-5 |
| 4 P-4 | 2 P-4 |
| 3 P-3 | 3 P-3 |
| 1 P-2 | 3 NPO |
| 9 LL | 7 LL |
| 22 | 17 |

Total: 39

Abbreviations: FS, Field Service; LL, Local level; NPO, National Professional Officer; RB, regular budget; USG, Under-Secretary-General; XB, extrabudgetary.

B.	Proposed organizational structure and post distribution for 2026

Office of the Executive Secretary

(executive direction and management)

| RB: | XB: |  |  |
| --- | --- | --- | --- |
| 1 USG | 4 LL |  |  |  |
| 2 D-2 |  |  |  |  |
| 1 D-1 |  |  |  |  |
| 2 P-5 |  |  |  |  |
| 2 P-4 |  |  |  |  |
| 1 P-3 |  |  |  |  |
| 1 P-2 |  |  |  |  |
| 8 LL |  |  |  |  |

18             4

Total: 22

Decision Support and Data Science Division

(executive direction and management)

| RB: | XB: |
| --- | --- |
| 1 P-5 | 3 LL |
| 1 P-4 |  |
| 1 P-3 |  |
| 1 P-2 |  |
| 8 LL |  |
| 12 | 3 |

Total: 15

Strategy, Planning, Accountability, Results and Knowledge Section

(executive direction and management)

RB:

1 P-5

1 P-4

1 P-3

1 P-2

6 LL

Total: 10

Resource Mobilization and Partnerships Section

(executive direction and management)

RB:

1 P-4

1 P-2

1 LL

Total: 3

Resource Management and Service Development Division

(programme support)

| RB: | XB: |
| --- | --- |
| 1 D-1 | 1 P-4 |
| 3 P-5a | 1 P-3 |
| 1 P-4a | 1 NPO |
| 3 P-3 | 15 LL |
| 3 P-2 |  |
| 1 FS |  |
| 2 NPOb |  |
| 38 LL |  |
| 52 | 18 |

Total: 70

Knowledge Management Service (executive direction and management)

| RB: |  |
| --- | --- |
| 1 P-5a |  |
| 6 P-4b |  |
| 4 P-3b |  |
| 1 NPOb |  |
| 18 LLb |  |

Total: 30

Cluster 1: Climate change and natural resource sustainability

(subprogramme 1)

| RB: | XB: |
| --- | --- |
| 1 D-1 | 1 D-1 |
| 4 P-5 | 1 P-5 |
| 4 P-4 | 2 P-4 |
| 3 P-3 | 1 P-3 |
| 1 P-2 | 3 NPO |
| 9 LL | 7 LL |
| 22 | 15 |
| Total: 37 |  |

Cluster 6: Governance and conflict prevention

(subprogramme 6)

RB:

1 D-1

3 P-5

4 P-4

2 P-3

1 P-2

6 LL

Total: 17

Cluster 2: Gender justice, population and inclusive development (subprogramme 2)

| RB: | XB: |
| --- | --- |
| 1 D-1 | 1 P-2 |
| 5 P-5 | 1 LL |
| 5 P-4 |  |
| 4 P-3 |  |
| 4 P-2 |  |
| 10 LL |  |
| 29 | 2 |

Total: 31

Cluster 3: Shared economic prosperity

(subprogramme 3)

| RB: | XB: |
| --- | --- |
| 1 D-1 | 1 P-3 |
| 2 P-5 | 2 LL |
| 5 P-4 |  |
| 5 P-3 |  |
| 2 P-2 |  |
| 12 LL |  |
| 27 | 3 |

Total: 30

Cluster 4: Statistics, the information society and technology

(subprogramme 4)

RB:

1 D-1

3 P-5

4 P-4

4 P-3

2 P-2

1 NPO

12 LL

Total: 27

Cluster 5: 2030 Agenda and SDG coordination

(subprogramme 5)

RB:

1 D-1

1 P-5

2 P-4

2 P-3

1 P-2

3 LL

Total: 10

Abbreviations: FS, Field Service; LL, Local level; NPO, National Professional Officer; RB, regular budget; USG, Under-Secretary-General; XB, extrabudgetary.

a	Reflects the reclassification of one P-4 post to a P-5 post.

b	Reflects the redeployment of one National Professional Officer post.

Annex II

Summary of proposed post changes, by component and subprogramme

| Component/subprogramme | Posts | Grade | Description | Reason for change |
| --- | --- | --- | --- | --- |
| Executive direction and management |  |  | Redeployment of the following posts from programme support: | The proposed inward redeployment of 30 posts relates to the proposed redeployment of the Conference Management Section as the Knowledge Management Service under executive direction and management, which would facilitate closer integration with ESCWA strategic planning and project cycles, fostering agility and responsiveness to ESCWA programmatic needs. Such structural realignment would ensure that knowledge management expertise in communication, content quality and multilingual support is more directly applied to enhance the mission of ESCWA and uphold its visibility and cohesion as a knowledge-driven organization. |
|  | 1 | P-5 | 1 Chief of Section, Conference Services |  |
|  | 6 | P-4 | 3 Reviser, Arabic; 1 Translator, English; 1 Editor, English; 1 Reviser |  |
|  | 4 | P-3 | 1 Translator, Arabic; 1 Editor, Arabic; 1 Editor, English; 1 Conference Services Officer |  |
|  | 1 | NPO | 1 Assistant Document Management Officer |  |
|  | 18 | LL | 1 Senior Language Reference Assistant; 1 Senior Editorial Assistant; 1 Senior Documents Management Assistant; 1 Editorial and Desktop Publishing Assistant; 1 Printing Press Operator; 1 Library Assistant; 2 Language Service Assistant; 2 Graphic Design Assistant; 2 Documents Management Assistant; 2 Administrative Assistant; 1 Desktop Publishing Assistant; 1 Offset Press Operator; 2 Assembly and Binding Equipment Assistant |  |
|  | (1) | NPO | Redeployment of 1 Programme Management Officer | The proposed outward redeployment would consolidate the quality-, oversight-, analytics- and assurance-related capacity under the programme support component, which would strengthen quality management and assurance over organizational matters in ESCWA. The redeployment is proposed in the context of a broader strategy within the programme support component reflecting enhanced overall management efforts through improved management of human and financial resources through the Resources Management Section and the increased overall emphasis on quality, oversight, assurance and analytics through the consolidation of related capacity under the Quality Management Section. |
| Programme support |  |  | Redeployment of the following posts from programme support: | See above reason for redeployments under executive direction and management. |
|  | (1) | P-5 | 1 Chief of Section, Conference Services |  |
|  | (6) | P-4 | 3 Reviser, Arabic; 1 Translator, English; 1 Editor, English; 1 Reviser |  |
|  | (4) | P-3 | 1 Translator, Arabic; 1 Editor, Arabic; 1 Editor, English; 1 Conference Services Officer |  |
|  | (1) | NPO | 1 Assistant Document Management Officer |  |
|  | (18) | LL | 1 Senior Language Reference Assistant; 1 Senior Editorial Assistant; 1 Senior Documents Management Assistant; 1 Editorial and Desktop Publishing Assistant; 1 Printing Press Operator; 1 Library Assistant; 2 Language Service Assistant; 2 Graphic Design Assistants 2 Documents Management Assistant; 2 Administrative Assistant; 1 Desktop Publishing Assistant; 1 Offset Press Operator; 2 Assembly and Binding Equipment Assistant |  |
|  | 1 | NPO | Redeployment of one Programme Management Officer | See above reason for the redeployment under executive direction and management. |
|  | (1) 1 | P-4 P-5 | Reclassification of a Medical Officer (P-4) to Senior Medical Officer (P-5) | The proposed reclassification reflects the expanding role of the Medical Officer on policy-driven initiatives, necessitating high-level representation in key United Nations working groups, including the United Nations Medical Directors Network, the global mental health team leadership and the United Nations country team occupational safety and health committee, in particular during crises. It also plays a pivotal role in the common back office planning for Lebanon, ensuring the continuity of medical services across the region. In addition, the post is responsible for continuous health and psychosocial risk assessments and developing health risk mitigation strategies for pandemics, infectious diseases and work-related incidents. The proposed model for ESCWA resembles other commissions, bearing in mind the security instability affecting the national healthcare system, which requires continuing mitigation support to bridge the gap and respond in a timely manner to support the needs of ESCWA staff in normal and/or crisis situations, which involves the following: (a) Regular visits/coordination with the national hospitals/healthcare providers, the Ministry of Public Health and the World Health Organization national office; (b) Regular hospital assessments in the region for potential casualty and medical evacuations to both national and international staff with their eligible dependents. In addition, The P-4 post was originally established to oversee medical issues of ESCWA staff only. However, the current security situation in the country and the leading role of ESCWA in the region, has required the post to manage an additional Medical Officer (National Professional Officer), along with one Nurse (Local level), one Staff Assistant (Local level) and a part time stress counsellor for United Nations entities within the Lebanon north Litani River duty station and other entities in the region, namely, offices of the resident coordinator, Secretariat offices and the International Renewable Energy Agency. |

Abbreviations: LL, Local level; NPO, National Professional Officer.